## Sheet1
Department | Department Head | Domain | Portfolio | Portfolio Owner | Project Name | Project Owner | Business Team | Project Status | Phase | Milestone | Start Date | Target Completion | Dependencies | Milestone Department | Milestone Owner | Current Status | Key Risks | Comments | Impact
IT | Karthick Raja S | IT Enabled | Digital Applications | S N Aditya Murthy | ESG Portal | Srihari Chellu | EHS & Sustainability | On Track | Define | User Requirement Specifications | 2025-10-16 | 2025-11-03 |  | EHS & Sustainability | P Latchi Reddy | Completed
IT | Karthick Raja S | IT Enabled | Digital Applications | S N Aditya Murthy | New CRM Implementation |  |  | On Track |  | Request for Proposal | 2025-11-04 | 2025-11-11 | User Requirement Specifications | IT | Srihari Chellu | Completed
IT | Karthick Raja S | IT Enabled | Digital Applications | S N Aditya Murthy | New CRM Implementation |  |  | On Track |  | Vendor Demo | 2025-11-12 | 2025-12-02 | Request for Proposal | IT | Srihari Chellu | Completed
IT | Karthick Raja S | IT Enabled | Digital Applications | S N Aditya Murthy | New CRM Implementation |  |  | On Track |  | Technical Assessment | 2025-12-03 | 2025-12-22 | Vendor Demo | IT | Srihari Chellu | Completed
IT | Karthick Raja S | IT Enabled | Digital Applications | S N Aditya Murthy | New CRM Implementation |  |  | On Track |  | Functional Assessment | 2025-12-23 | 2025-12-22 | Vendor Demo | EHS & Sustainability | P Latchi Reddy | Completed
IT | Karthick Raja S | IT Enabled | Digital Applications | S N Aditya Murthy | New CRM Implementation |  |  | On Track |  | Comparison Matrix | 2025-12-23 | 2026-01-01 | Technical Assessment, Functional Assessment | EHS & Sustainability, IT | P Latchi Reddy, Srihari Chellu | Completed
IT | Karthick Raja S | IT Enabled | Digital Applications | S N Aditya Murthy | New CRM Implementation |  |  | On Track |  | Project Charter | 2026-01-02 | 2026-01-11 | Comparison Matrix | IT | Srihari Chellu | Completed
IT | Karthick Raja S | IT Enabled | Digital Applications | S N Aditya Murthy | New CRM Implementation |  |  | On Track |  | Commercial Negotiation | 2026-01-12 | 2026-02-11 | Project Charter | Procurement | Vijay Kumar Raju Kusampudi | Completed
IT | Karthick Raja S | IT Enabled | Digital Applications | S N Aditya Murthy | New CRM Implementation |  |  | On Track |  | Note for Approval | 2026-02-12 | 2026-02-22 | Commercial Negotiation | IT | Srihari Chellu | Completed
IT | Karthick Raja S | IT Enabled | Digital Applications | S N Aditya Murthy | New CRM Implementation |  |  | On Track |  | Purchase Order | 2026-02-23 | 2026-03-04 | Note for Approval | EHS & Sustainability, IT | P Latchi Reddy, Srihari Chellu | Completed
IT | Karthick Raja S | IT Enabled | Digital Applications | S N Aditya Murthy | New CRM Implementation |  |  | On Track |  | Master Service Agreement | 2026-03-05 | 2026-03-15 | Note for Approval | IT, Legal | Srihari Chellu, Debleena Ray | Completed
IT | Karthick Raja S | IT Enabled | Digital Applications | S N Aditya Murthy | New CRM Implementation |  |  | On Track | Design | Technical Design | 2026-03-16 | 2026-03-30 | Purchase Order, MSA | IT | Srihari Chellu | Completed
IT | Karthick Raja S | IT Enabled | Digital Applications | S N Aditya Murthy | New CRM Implementation |  |  | On Track |  | Functional Design | 2026-03-16 | 2026-03-30 | Purchase Order, MSA | EHS & Sustainability | P Latchi Reddy | Completed
IT | Karthick Raja S | IT Enabled | Digital Applications | S N Aditya Murthy | New CRM Implementation |  |  | On Track | Develop | Configurations / Customizations | 2026-03-31 | 2026-05-30 | Technical Design, Functional Design | IT | Srihari Chellu | Completed
IT | Karthick Raja S | IT Enabled | Digital Applications | S N Aditya Murthy | New CRM Implementation |  |  | On Track |  | Unit Testing | 2026-05-31 | 2026-06-12 | Configurations / Customizations | IT | Srihari Chellu | In Progress
IT | Karthick Raja S | IT Enabled | Digital Applications | S N Aditya Murthy | New CRM Implementation |  |  | On Track | Detect | User Acceptance Testing | 2026-06-10 | 2026-07-05 | Unit Testing | EHS & Sustainability | P Latchi Reddy | Not Started
IT | Karthick Raja S | IT Enabled | Digital Applications | S N Aditya Murthy | New CRM Implementation |  |  | On Track | Deploy | Go Live | 2026-07-06 | 2026-07-15 | User Acceptance Testing | EHS & Sustainability | P Latchi Reddy | Not Started