# Project Hub (PMO) — Full Technical & User Guide

Granules AI-Powered Platform · apps/pmo · Web :5182 / API :3008

2026-06-24

Table of Contents

# 1	1. Introduction

## 1.1	1.1 What Project Hub is

Project Hub (codename pmo, source tree apps/pmo) is the Granules enterprise Project & Portfolio Management (PPM) application. It runs the full project lifecycle end to end — demand intake → procurement → execution → go-live → closure — with hard, server-enforced governance gates, an approval engine, automatic escalations, RFx procurement with sealed bids, and portfolio reporting, all wrapped in a Monday.com-style work-management UX (WBS tree, board, table, Gantt, calendar, rollups). An embedded read-only AI analyst, NYRA, answers questions over live portfolio data.

Two design pillars govern everything:

- Governance is authoritative. Stage advancement, approvals, RBAC, escalations and procurement are enforced server-side. The Monday-style UI sits on top of these rules and never bypasses them.

- Computed progress is the source of truth; RAG is human. progress_pct rolls up automatically Subtask → Task → Milestone → Project → Portfolio. RAG health and gate approvals stay deliberate PM/PMO judgments and are never auto-written.

## 1.2	1.2 Where it sits in the Granules suite

Project Hub is a sibling app under apps/ alongside Portal (5173/3002), Recruit (5174/3001), PMS (5175/3003), OHC (5176/3004) and Careers (5179). It:

- Shares the Master Employee DB for SSO — the same JWT auth as every other Granules app, gated by the access_pmo flag in employee_auth.

- Shares the Recruit Supabase DB for storage — its tables are all pmo_-prefixed and coexist with the recruiting tables in the same Postgres public schema (which is exactly why NYRA’s SQL is hard-walled to pmo_* tables).

- Uses the same Anthropic OAuth / LLM stack and the same SMTP account (nyra@granulesindia.com, Office 365).

- Integrates outward to Jira (two-way task sync), Microsoft Teams (meeting MoM ingest) and SAP (PR/PO sync).

- Is independently runnable and must not break the other apps.

LAN access URL: http://172.30.101.2:5182

# 2	2. Architecture

## 2.1	2.1 Layers

| Layer | Detail |
| --- | --- |
| Frontend | artifacts/project-hub/ — React 18 + TypeScript + Vite 7 + Tailwind. Routing via wouter, data via TanStack React Query, light global state via zustand (lib/store.ts). Dev server port 5182 (requires PORT + BASE_PATH env). |
| Backend API | artifacts/api-server/ — Node + Express 5 + TypeScript, esbuild-bundled to dist/index.mjs. Port 3008. |
| Shared DB lib | lib/db/ — Drizzle ORM schema package (@workspace/db). Canonical schema source is lib/db/src/schema/ (≈ 41–49 files, ~63 pmo_* tables). esbuild bundles this lib from src, so schema edits are live without a dist rebuild. |
| API types | lib/api-zod/ (@workspace/api-zod) — zod request/response schemas; the generated React Query client is @workspace/api-client-react. |
| LLM | @workspace/llm workspace package — the single AI entrypoint (llm() / llmWithTools()); routes never instantiate a provider directly. |
| Data DB | Recruit Supabase DB (rhhpmohhxlmylrnzdcoe, aws-1-ap-northeast-1 pooler) — all pmo_* tables. |
| Auth DB | Master Employee DB (loqyxdhkfjnuaykxxwis) — JWT validation + employees + employee_auth access flags. |
| Vendor auth DB | Separate Supabase project for the external vendor portal (email-OTP login, distinct from employee auth; currently reuses the Recruit/candidate project as a documented fallback). |

## 2.2	2.2 Request path

Browser
  → Vite dev server (5182, proxies /api → http://localhost:3008)
    → Express (3008)
        requireAuth  (Bearer JWT validated vs Master DB; gate on access_pmo)
        → routes (/api/...)
          → Drizzle ORM
            → Recruit Supabase DB (pmo_* tables)

Vite proxies the /api prefix to the PMO backend (API_TARGET override). One special family — /api/org, /api/action-items, /api/kpi-approvers — is proxied to a separate org backend (CXO_TARGET), used by the “My Team Actions” page.

## 2.3	2.3 Source tree (the real code is under artifacts/)

apps/pmo/
├── artifacts/
│   ├── api-server/        # Express backend → dist/index.mjs (port 3008)
│   │   └── src/
│   │       ├── app.ts            # Express app + middleware + router mounting
│   │       ├── index.ts          # process entrypoint, registers jobs, listens
│   │       ├── middlewares/      # requireAuth, requireVendorAuth
│   │       ├── routes/           # ~50 route files + admin/, integrations/
│   │       ├── lib/              # gates, rollup, critical path, notify, nyraSql, …
│   │       └── jobs/             # 5 scheduled background jobs
│   ├── project-hub/       # React SPA (port 5182)
│   │   └── src/
│   │       ├── App.tsx           # wouter router + global overlays
│   │       ├── auth/             # AuthConsumer (SSO), context, types
│   │       ├── pages/            # ~46 routed pages
│   │       ├── components/       # monday/, ui-kit/, dashboard/, stage-sections/, …
│   │       └── lib/              # store, extra-api, lifecycle-config, supabase
│   ├── mockup-sandbox/    # auxiliary
│   └── public/
├── lib/
│   ├── db/                # @workspace/db — Drizzle schema (pmo_* tables)
│   ├── api-zod/           # @workspace/api-zod — request/response schemas
│   └── api-client-react/  # generated React Query hooks
├── scripts/               # hand-written SQL migrations, seeds, .docx generators
├── document-templates/    # 15 mandatory lifecycle deliverable templates
└── migrations/            # older duplicate .ts schema (NOT the live source)

## 2.4	2.4 Build & runtime model

- The API runs from the bundled dist/index.mjs, so backend source edits require node ./build.mjs + restart. Exception: the @workspace/db lib bundles from src, so schema edits are live.

- The frontend is Vite HMR — frontend edits are live, no restart.

- Do not run drizzle-kit push against the shared Recruit DB — apply schema changes via the hand-written idempotent SQL in scripts/ (e.g. migrate-stages-1-6.sql, add-doa-matrix-and-merge-charter-nfa.sql).

- When restarting via shell, never pkill -f 'dist/index.mjs' from a command whose own text contains that string — it self-kills the shell.

# 3	3. Running & operating

# API server — from apps/pmo/artifacts/api-server  (reads env from the PROCESS)
node ./build.mjs            # esbuild bundle → dist/index.mjs
pnpm run start              # node --enable-source-maps ./dist/index.mjs   (PORT=3008)
pnpm run dev                # = build + start, NODE_ENV=development

# Frontend — from apps/pmo/artifacts/project-hub  (HMR, no rebuild needed)
PORT=5182 BASE_PATH=/ pnpm run dev
pnpm run build && pnpm run serve    # production preview

Workspace packages are pnpm filters: pnpm --filter @workspace/api-server run dev, pnpm --filter @workspace/project-hub run dev.

## 3.1	3.1 Feature flags (default OFF)

- ENABLE_SCHEDULER=true — turns on the 5 background jobs (escalations, nudges, SAP/Teams sync). Off in dev and for multi-replica deployments.

- AUTO_ESCALATION_EMAILS=on — lets the automated jobs send escalation email. In-app notifications always fire; manual Remind/Escalate buttons always email regardless of this flag.

## 3.2	3.2 Operational gotchas

- Backend source edit → rebuild + restart (except @workspace/db).

- Most governance roles need a person assigned in /admin/role-directory before escalation recipients resolve.

- Closed projects are read-only across the API.

# 4	4. Configuration (environment keys)

Key names only — no values are reproduced here. The API server reads env from the process at start. The frontend reads VITE_* vars at build/dev time.

## 4.1	4.1 Data & auth databases

| Key | Configures |
| --- | --- |
| DATABASE_URL | Recruit Supabase pooler — the data DB holding all pmo_* tables. |
| MASTER_DB_URL, MASTER_DB_SERVICE_ROLE_KEY | Master Employee DB — SSO / JWT validation + employee_auth RBAC. |
| SUPABASE_URL, SUPABASE_SERVICE_ROLE_KEY | Supabase service client (shared DB operations). |
| VENDOR_AUTH_DB_URL, VENDOR_AUTH_DB_SERVICE_ROLE_KEY | Vendor-portal Supabase project (email-OTP login). |
| SESSION_SECRET | express-session secret (dev role simulator). |
| NODE_ENV, LOG_LEVEL, PORT | Standard runtime config. PORT is 3008 in live config. |

## 4.2	4.2 AI / mailer / integration

| Key | Configures |
| --- | --- |
| ANTHROPIC_API_KEY | Claude OAuth token (sk-ant-oat*) — powers AI drafts, insights and the NYRA tool loop. |
| LLM_DEFAULT_MODEL | Model id, default claude-sonnet-4-6. |
| SMTP_HOST, SMTP_PORT, SMTP_SECURE, SMTP_USER, SMTP_PASS, FROM_EMAIL, FROM_NAME | Outbound notification email + Teams email-to-channel posts (Office 365). |
| PMO_BASE_URL | Absolute link base for emails / Teams posts. |
| ENABLE_SCHEDULER, AUTO_ESCALATION_EMAILS | Background-job + auto-email flags (see §3.1). |
| PMO_DOC_PUSH_TOKEN | Shared secret for tech-team PUT /api/documents/:id/raw push + document share tokens. |
| PMO_MCP_TOKEN, PMO_MCP_ACTORS | PMO MCP service-token (“act-as”) auth + actor allowlist. |

## 4.3	4.3 Frontend (Vite) keys

| Key | Configures |
| --- | --- |
| VITE_MASTER_DB_URL, VITE_MASTER_DB_ANON_KEY | Browser Supabase client (Master DB session). |
| VITE_PORTAL_LOGIN_URL | Where unauthenticated users redirect to log in (Portal /login). |
| PORT, BASE_PATH | Dev server port (5182) + base path. |

SAP credentials are not in env (SAP runs in mock mode by default; SAP_MODE=real would switch the adapter). Teams is mock-first and posts via the SMTP email-to-channel path (teamsChannelEmail on the project) rather than a Graph token.

# 5	5. Frontend

## 5.1	5.1 Routing & global shell

Router file: src/App.tsx — a wouter <Switch> inside <Layout>, base import.meta.env.BASE_URL. React Query defaults: staleTime 30s, refetchOnWindowFocus false, retry 1. Every route change calls noteNav() so the in-app Back button knows whether to pop or fall back.

Global overlays mounted once in App.tsx: <Toaster>, <TitleTooltip>, <SessionExpiredModal>, <JustificationRequiredModal>, <AskNyra>.

### 5.1.1	Full route → page map (wouter matches top-down)

| Route | Page component | File |
| --- | --- | --- |
| / | redirect → /portfolio | — |
| /charters/new | NewCharterTemplate | pages/charter-template-new.tsx |
| /charters | ChartersList | pages/charters.tsx |
| /charter-nfa | CharterNfaSelect | pages/charter-nfa-select.tsx |
| /demands/new | NewDemand | pages/demand-new.tsx |
| /demands | DemandsList | pages/demands.tsx |
| /pipeline | PipelinePage | pages/pipeline.tsx |
| /issues | IssuesList | pages/issues.tsx |
| /charters/:id | CharterDetail | pages/charter-detail.tsx |
| /approvals | ApprovalsList | pages/approvals.tsx |
| /my-team-actions | MyTeamActions | pages/my-team-actions.tsx |
| /projects | ProjectsList | pages/projects.tsx |
| /projects/tree | ProjectsTreeView | pages/projects-tree.tsx |
| /projects/:id/tasks/new | NewTask | pages/task-new.tsx |
| /projects/:id | ProjectDetail | pages/project-detail.tsx |
| /portfolio | PortfolioOverview (default landing) | pages/portfolio-overview.tsx |
| /portfolio-legacy | PortfolioView | pages/portfolio.tsx |
| /my-tasks | MyTasksPage | pages/my-tasks.tsx |
| /resources | ResourceManagement | pages/resource-management.tsx |
| /tasks | TasksPage | pages/tasks.tsx |
| /admin/scoring | AdminScoring | pages/admin-scoring.tsx |
| /admin/stage-slas | AdminStageSlas | pages/admin-stage-slas.tsx |
| /admin/role-directory | AdminRoleDirectory | pages/admin-role-directory.tsx |
| /admin/roles | AdminRoles | pages/admin-roles.tsx |
| /admin/cip | AdminCip | pages/admin-cip.tsx |
| /admin/stage-escalation | AdminStageEscalation | pages/admin-stage-escalation.tsx |
| /admin/doa-matrix | AdminDoaMatrix | pages/admin-doa-matrix.tsx |
| /admin/integrations | AdminIntegrationsPage | pages/admin-integrations.tsx |
| /documents | DocumentsPage | pages/documents.tsx |
| /lessons-learned | LessonsLearnedPage | pages/lessons-learned.tsx |
| /templates | TemplatesPage | pages/templates.tsx |
| /pifs/new | PifNew | pages/pif-new.tsx |
| /pifs/:id | PifDetail | pages/pif-detail.tsx |
| /pifs | PifsList | pages/pifs.tsx |
| /nudges | NudgesPage | pages/nudges.tsx |
| /automations | AutomationsPage | pages/automations.tsx |
| /activity | ActivityPage | pages/activity.tsx |
| /vendors/new | VendorNewPage | pages/vendor-new.tsx |
| /vendors/scorecards | VendorScorecardsPage | pages/vendor-scorecards.tsx |
| /vendors/:id | VendorDetailPage | pages/vendor-detail.tsx |
| /vendors | VendorsPage | pages/vendors.tsx |
| /rfx/new | RfxNewPage | pages/rfx-new.tsx |
| /rfx/:id | RfxDetailPage | pages/rfx-detail.tsx |
| /rfx | RfxListPage | pages/rfx-list.tsx |
| (fallback) | NotFound | pages/not-found.tsx |

pages/dashboard.tsx (internal role-routing shell) and pages/project-detail.legacy.tsx (dead code, ~105 KB) are not routed.

### 5.1.2	Layout & header — components/Layout.tsx

Two-column shell: <PmoSidebar> on the left, a suite-shared <AppHeader> on top, scrollable #ph-content page area. The header hides its own search and profile chip (identity moves to the sidebar foot). Header actions: ThemeToggle, <NotificationBell>, a Connectors plug button (admins → ConnectorsPopup), and a Settings gear linking to /admin/scoring. leftSlot is a portal target #ph-topbar-slot into which pages (notably Portfolio Overview) inject their filters. ADMIN_ROLES = ["pmo","executive_director","chairman"] drives isAdmin; isSuperAdmin comes from profile.is_super_admin. On mount the header calls GET /api/users/me and syncs the role into the zustand store.

### 5.1.3	Sidebar — components/PmoSidebar.tsx

Wraps the suite-shared CollapsibleSidebar. App name “Project Hub”, logo links to /portfolio. Collapsed state persisted in localStorage (ph:sidebar:collapsed). Two sentinel hrefs are intercepted (they don’t route): #charter-nfa (→ /charters) and #business-case (→ opens CharterNfaPopup). Nav structure:

- Top group — Business Case (CTA pill, opens chooser) · Portfolio (/portfolio) · Projects (/projects) · Charter + e-NFA (#charter-nfa→/charters) · My Tasks (/my-tasks) · My Team Actions (/my-team-actions)

- Vendor Evaluation (collapsible) — New RFP (/rfx) · Vendor on board (/vendors)

- Group — Approvals (/approvals) · Risks / Issues (/issues) · Resource Management (/resources)

- Workspace (collapsible) — My Activities (/activity) · Automations (/automations) · Document Repository (/documents) · Lessons Learned (/lessons-learned) · Nudges (/nudges) · Connectors (/admin/integrations)

- Admin (only if isAdmin) — Scoring Config (/admin/scoring) · Stage SLAs (/admin/stage-slas) · Role Directory (/admin/role-directory) · Escalation Ladders (/admin/stage-escalation) · DOA Matrix (/admin/doa-matrix)

- Super-admin group (only if isSuperAdmin) — Roles & Access (/admin/roles) · CIP (/admin/cip)

## 5.2	5.2 Authentication (frontend)

Project Hub is a read-only SSO consumer — it has no login UI; it consumes an existing Supabase session created by the Portal.

- lib/supabase.ts — Master DB browser client via @supabase/ssr createBrowserClient, cookies scoped to .granulesrecruit.com / .mygranules.com so one Portal login hydrates every subdomain. On localhost/LAN-IP the session falls back to per-origin localStorage. getFreshToken() force-refreshes tokens within 60 s of expiry. getPortalLoginUrl() derives the Portal /login URL from the current host.

- auth/AuthConsumer.tsx — provider mounted at app root. On mount: (1) getSession(); no session or session older than the 8-hour timeout → redirect to Portal login with a ?redirect= back-URL. (2) fetchProfile(userId, email) reads Master DB employees (then contractual_employees) joined to employee_auth(access_pmo, pmo_role, is_admin, is_super_admin) by office_email. (3) Gate: no profile → denial screen; profile but !access_pmo && !is_super_admin → denial screen. (4) On success, fire-and-forget hydrateLocalUser() → GET /api/users/me (auto-provisions a pmo_users row) and seeds the zustand store.

- auth/context.ts — useAuth() exposes { user, profile, loading, profileReady, signOut }.

How roles gate the UI: two layers. (a) The Supabase profile gates app access and the super-admin sections. (b) A separate effective/simulated role in useUserStore (lib/store.ts, default "initiator"), synced from GET /api/users/me’s pmoRole, drives workflow affordances — e.g. in charter-detail.tsx: canEdit = status==="draft" && role==="initiator", canScmNegotiate = role==="scm", canFinanceOrder = role==="finance", canCreateProject = role==="pmo". Authorization is always enforced server-side off the real role; the client role only toggles affordances.

Authenticated fetch: src/main.tsx installs the shared fetch interceptor — injects Authorization: Bearer <token> on /api/ URLs and dispatches granules:session-expired on 401 (surfaced by <SessionExpiredModal>).

## 5.3	5.3 Pages by group

### 5.3.1	A. Projects

- /projects (projects.tsx) — main board (largest page). Toolbar: expandable Search, view switcher Table · Kanban · Gantt, icon filters Status / Priority / Department, column show/hide, Jira import. Kanban drag across columns opens MoveJustifyModal (justification required before a status change persists). Data: useListProjects/Users/Charters/AllProjectTeamMembers + /api/projects/:id/tasks rollups.

- /projects/:id (project-detail.tsx) — per-project workspace. Header buttons: Documents (versioned, stage-organised repo modal) and Live Project Report (POST /api/ai/projects/:id/live-charter). Section switcher Tasks · Team. Tasks view switcher Overview · Table · Kanban · Gantt · Calendar; tasks grouped by milestone in an inline-edit spreadsheet (ExcelGroupTable) with status/priority/owner/timeline/progress/subtasks/dependency cells; rows expand to subtasks; click opens TaskDetailModal; per-task TaskCommsDrawer, project-level ProjectCommsDrawer. Team section renders TeamTab (members + RACI).

- /projects/tree (projects-tree.tsx) — Portfolio → Program → Project tree.

- /tasks (tasks.tsx) — global cross-project task list; six views Tree · Board · Kanban · Table · Timeline · Calendar; TaskFilterBar.

- /projects/:id/tasks/new (task-new.tsx) — New Task form (useCreateTask).

- /my-tasks (my-tasks.tsx) — personal buckets (Overdue / Due Today / Waiting Approval / Upcoming / Assigned) from GET /api/me/tasks.

- /my-team-actions (my-team-actions.tsx) — manager view on a separate org backend (/api/org, /api/action-items, /api/kpi-approvers): department filter, people search, team summary, org-subtree drill, owner task buckets.

- /resources (resource-management.tsx) — capacity/allocation across projects.

### 5.3.2	B. Charters / NFA

- /charter-nfa (charter-nfa-select.tsx) — “Start a Business Case” chooser: Project Charter / e-NFA for projects vs e-NFA for non projects (both → /charters/new). Also appears as the CharterNfaPopup from the sidebar CTA.

- /charters (charters.tsx) — Kanban of charters, filter tabs All · Draft · In Review · Approved · Active; columns Draft → Submitted → Parallel Review → SCM Review → Chairman Review → Finance Review → PMO Review → Approved → Active → Rejected.

- /charters/new (charter-template-new.tsx) — AI charter wizard, two-step pill stepper Project Charter · e-NFA: step 1 upload/extract from a reference doc (POST /api/ai/charters/extract-fields) or AI-draft (/draft-template); step 2 review/edit all fields before create.

- /charters/:id (charter-detail.tsx) — viewer + workflow driver. Header: status badge, Charter+e-NFA (.docx) download (GET /api/charters/:id/docx), role-gated actions Edit / Submit for Approval / Create Project / Enter Negotiated Price (SCM) / Enter SAP Order (Finance). Tabs: Details (inline docx via DocxView), Vendors, Benefits, Risks, Squad, Approvals (sign-off timeline).

### 5.3.3	C. Demand / PIF / RFx

- /pifs (pifs.tsx) — Project Initiation Forms (Stage 0). Status tiles Drafts / Awaiting HOD / Approved / Converted / Rejected.

- /pifs/new (pif-new.tsx) — New PIF; “Draft with AI” (POST /api/ai/pif/draft-from-idea) fills the form; sections Basics / Outcomes & metrics / Dependencies & risks / Cost & timeline.

- /pifs/:id (pif-detail.tsx) — viewer; Submit (/submit), AI readiness check, HOD Approve/Reject (/decide), Convert to project.

- /demands (demands.tsx) — Active Demands (pre-charter, stages initiation + vendor_selection); 4 stage tiles.

- /demands/new (demand-new.tsx) — “Business Case” (Stage 1); name + AI-drafted description (/api/ai/demand/draft-idea, /api/ai/improve-text); creates project + initiation stage.

- /pipeline (pipeline.tsx) — 4-phase pipeline (PhaseLane → GateCard per stage) from /api/dashboard/critical-path-portfolio + /initiation-subgates.

- /rfx (rfx-list.tsx) — sourcing events (RFI/RFP/RFQ/e-auction); per-row Float to vendors (publish + invitations) and delete.

- /rfx/new (rfx-new.tsx) — New RFx form (type, currency, title, brief, closes-at, commercial threshold %, surrogate/alternative toggles).

- /rfx/:id (rfx-detail.tsx) — RFx workspace (polls 15 s): QuestionsPanel, DimensionsPanel, VendorsPanel, BidsPanel (dual-role unlock), ScoringPanel (blind grading), AwardPanel (split share %), AuditPanel; Download RFP, Publish.

### 5.3.4	D. Vendors

- /vendors (vendors.tsx) — Vendor Master; search + Segment + Risk filters; table with segment/risk badges.

- /vendors/new (vendor-new.tsx) — manual registration form.

- /vendors/:id (vendor-detail.tsx) — profile; inline segment + risk-status selects; tabs Profile · Documents · Qualifications · KPIs · Risk (verify docs, add KPIs/qualifications/risk events).

- /vendors/scorecards (vendor-scorecards.tsx) — composite-KPI scorecard grid.

### 5.3.5	E. Admin

- /admin/scoring — Scoring Configuration (weighted criteria + ProjectScoringModal).

- /admin/stage-slas — per-stage target days (PATCH /api/stage-slas/:stage).

- /admin/role-directory — assign each governance role to a person or group email.

- /admin/roles (super-admin) — Roles & Access RBAC: per-employee effective role (override vs derived) + access_pmo switch + Recent changes audit panel.

- /admin/cip (super-admin) — CIP special-projects timelines.

- /admin/stage-escalation — Escalation Ladders (per-stage tiers).

- /admin/doa-matrix — DOA bands (entity/category/kind × amount) + Resolve preview.

- /admin/integrations — Connectors (MCP + datasource CRUD, MCP live status).

### 5.3.6	F. Dashboards (pages/dashboard.tsx + pages/dashboards/*)

dashboard.tsx is an internal role-router that lazy-loads one of five dashboards by useUserStore().role, with MyWorkBoard on top:

- ExecutiveDashboard (executive_director/chairman/cfo) — portfolio-health, stuck-approvals, top risks, justifications, Top Strategic Projects.

- PortfolioDashboard (pmo/scm) — portfolio-health, scoring-rank, capacity-demand, stuck-approvals, critical-path-portfolio.

- PMDashboard (pm) — Health Index, task summary, due-this-week, overdue/blocked, pending approvals, my projects.

- FunctionalHeadDashboard (hod/finance) — delivery performance, RAG distribution, budget by project, resource conflicts.

- GeneralDashboard (default) — project health, charter status, speed champions, recent activity.

### 5.3.7	G. Misc / Workspace

- /portfolio (portfolio-overview.tsx) — default landing. Filters portaled into #ph-topbar-slot; sortable Portfolio Summary table with RAG/schedule health, leader/department grouping, problem projects, status bars; Drillable tiles. Calls /api/project-justifications/latest, /api/leadership/cmd-reports, /api/tasks, /api/departments, /api/users, POST /api/project-justifications/request.

- /portfolio-legacy (portfolio.tsx) — older RAG-distribution / budget-utilization board.

- /approvals (approvals.tsx) — Stage Approvals (InitiatorStageAdvancePanel → /stages/:stage/test-advance) + Charter Approvals chain; pending vs escalated lanes.

- /issues (issues.tsx) — Risks / Issues across all projects.

- /documents (documents.tsx) — Central Document Repository (versions, stages, access levels, share dialog).

- /lessons-learned — repository + AI Semantic Match (/api/ai/lessons-learned/search).

- /templates — Project Templates (instantiate, import JSON).

- /nudges — Your Nudges (dismiss / acted-on / bulk-dismiss).

- /automations — Escalation rules CRUD (writes real pmo_escalation_rules).

- /activity — reverse-chron activity feed grouped by day.

## 5.4	5.4 Shared components

Monday board kit — components/monday/: MondayBoard (grouped/expandable/dnd hierarchical table via @dnd-kit), KanbanView, CalendarView, ViewSwitcher, MyWorkBoard, cells.tsx (StatusCell/PriorityCell/OwnerCell/DateCell/ProgressCell/DependencyCell/…), useBoardColumns.ts. Plus monday-gantt.tsx and excel-group-table.tsx.

UI kit — components/ui-kit/: StatusChip family (HealthChip/StageChip/ApprovalChip/ToneChip), OwnerStrip, PhaseChip, MetricCard, PageHeader/SectionHeader, RephraseField, TitleTooltip, HoverHint.

Dashboard widgets — components/dashboard/primitives.tsx: MetricDrillModal, Drillable, RAGBadge/RAGDot, KPITile, SLACountdown, FilterBar, useAutoRefresh, DashboardCard, export helpers exportCSV/exportXLSX/exportPDF.

Lifecycle / stage: stage-panel.tsx (Overview · Documents · Checklist · Approvals; drives stage advance). components/stage-sections/ — 21 stage-specific sections (DemandInitiationSection, InitiationSubGates, URSDualApproval, RFPSection, VendorShortlist/VendorEvalScorecard, TechnicalDesignSection, ImplementationPlanSection, UATDefects, GoLiveCountdown, LegalSection, PRPOSection, NFASection, CharterSection, ClosureReadinessSection/ClosureReport, …). Lifecycle model in lib/lifecycle-config.ts + lib/lifecycle-phases.ts.

Project-detail tabs: charter-overview, project-overview, team-tab, raci-tab, resource-tab, budget-tab, risk-tab, benefits-tab, change-requests-tab, issues-tab, lessons-learned-tab, meetings-tab, messages-tab, documents-tab, procurement-tab, audit-tab, live-charter-tab, project-approvals-tab, milestone-grid, wbs-tree, sow-board, connect-board, effort-burn-chart, progress-tracking-panel.

Task components: task-detail-modal.tsx (Jira-style: description inline edit, subtasks, linked items, Activity tabs All/Comments/History/Work log, right sidebar details), task-grid, task-filter-bar, task-status-chip, log-time-modal, person-avatar, status-badge.

Drawers / modals: ProjectCommsDrawer, TaskCommsDrawer, MoveJustifyModal, JustificationRequiredModal, SessionExpiredModal, ShareDialog, issue-raise-modal, CharterNfaPopup, ConnectorsPopup, ReferenceDocUpload, CustomFieldsEditor, DocxView, notification-bell.

AI components: AskNyra.tsx (floating chat; POST /api/ai/ask; markdown + collapsible “N queries run” trace; hidden when AI not configured) and ai-button.tsx (AiButton + useAiStatus).

# 6	6. Backend

## 6.1	6.1 Server bootstrap & middleware

index.ts (entrypoint): imports app, the scheduler, and the 5 job runners. Reads PORT (throws if missing/invalid; live = 3008). Registers the 5 jobs (inert unless ENABLE_SCHEDULER=true), then app.listen(...) → startScheduler(). Listen error → log + process.exit(1).

app.ts middleware stack (in order):

- pino-http request logging (lib/logger).

- cors({ origin: true, credentials: true }) — reflects origin, allows credentials.

- express.json({ limit: "25mb" }) — bumped for base64 xlsx task-import bodies.

- express.urlencoded({ extended: true }).

- express-session — stores simulatedRole; secret from SESSION_SECRET; cookie secure in prod, httpOnly, sameSite strict(prod)/lax(dev), maxAge 24h.

Router mounting — public routers mount before the requireAuth gate so they bypass it:

- /api → vendorAuthRouter (vendor OTP, no auth)

- /api → vendorPortalRouter (/api/vendor/*, runs requireVendorAuth inside)

- /api → templateFilesRouter (public blank-template downloads)

- /api → localUploadsRouter (local-FS presigned PUT)

- /api → documentsPublicRouter (public per-doc RAW read + tech-team push)

- /api → requireAuth, router — everything else (the routes/index.ts aggregate)

routes/index.ts mounts ~45 sub-routers with no prefix (each declares its own paths), plus two prefixed: /admin/integrations and /admin/roles (the latter behind requireSuperAdmin).

## 6.2	6.2 Authentication & role derivation

middlewares/requireAuth.ts populates req.user: PmoUser (authUserId, email, employeeId, employeeCode, fullName, isAdmin, isSuperAdmin, accessPmo, pmoRole, seeAllProjects, viaServiceToken). Public bypass: /healthz (+ dev-only /session/role). Two auth paths:

- Service-token “act-as” (PMO MCP / automation): header X-PMO-Service-Token must equal PMO_MCP_TOKEN; requires X-PMO-Actor (employee code or office email). Fail-closed: PMO_MCP_ACTORS allowlist must be non-empty (else 503); "*" = any. Records writes via recordMcpWrite for POST/PUT/PATCH/DELETE.

- Standard JWT bearer: Authorization: Bearer <token> → masterDb.auth.getUser(token) → resolve employee by office email. 401 on missing/invalid/expired.

resolvePmoUser() queries Master DB employees joined employee_auth!inner(access_pmo, pmo_role, is_admin, is_super_admin). Gate: requires access_pmo OR is_super_admin (else 403). seeAllProjects = super-admin OR role ∈ {admin, chairman, executive_director} OR function==='transformation'.

Companion guards: requireAdmin (super-admin or pmoRole==='admin'), requireSuperAdmin (super-admin only — used for /admin/roles).

lib/derivePmoRole.ts — SSOT for functional pmoRole. Resolution order: (1) explicit override — employee_auth.pmo_role or a Recruit-DB pmo_role_overrides row (takes precedence), accepted only if a known role; (2) directory derivation from designation_text/business_designation + function + grade_code, most-specific first: chairman → executive_director → cfo → pmo → pm → hod → function+senior-grade scm/finance → fallback team_member. 10 roles: admin, chairman, executive_director, cfo, pmo, pm, hod, scm, finance, team_member (senior grade bands D–H).

lib/guard.ts — requireRole(...allowed) (runs after requireAuth): no user → 401; platform admin always allowed; "initiator" in allowed → any authenticated PMO user passes; else role must be in the list (403). Role-set constants:

- WRITE_ROLES = [pm, pmo, hod, initiator] (variants add scm for procurement, or finance for benefits).

- DECIDE_ROLES = [pmo, hod, cfo, chairman, executive_director, scm, finance] (change_requests DECIDE = [pmo, hod, cfo, chairman]).

- SCORING_ROLES = [pmo, executive_director, chairman]; BASELINE_ROLES = [pm, pmo]; deletes usually [pmo, pm] (+ scm for procurement).

middlewares/requireVendorAuth.ts — /api/vendor/* only. Validates Bearer JWT against the vendor-auth Supabase project, resolves a pmo_vendor_master row by auth_user_id, populates req.vendor. 401 missing/expired; 403 if no profile or segment==='blocked'.

lib/role-resolver.ts — resolveRole(role, projectId?) maps a governance role to people/emails: project-scoped roles {project_manager, pm, owner, sponsor} from project/charter fields; all others from pmo_role_directory. Returns [] (logged) when unresolved.

lib/doa-resolver.ts — resolveApproverChain(ctx) / matchBand(ctx) resolves the Charter+NFA approver chain from pmo_doa_matrix: filter active rows where amount ∈ [min, max) and entity/category/kind match exactly or *; score specificity (entity +4, category +2, kind +1); ties → tighter range → id. Returns ordered role strings.

## 6.3	6.3 Endpoints by domain

All paths relative to /api. [WRITE], [DECIDE], etc. denote requireRole guards; plain GETs need only requireAuth.

### 6.3.1	Health & session

- GET /healthz (public) · POST /session/role (dev-only, 403 in prod) · GET /session/role

### 6.3.2	Projects (projects.ts) — WRITE = pm/pmo/hod/initiator

- GET /projects · POST /projects [WRITE] · GET /projects/scoring-rank · GET /projects/:id · PATCH /projects/:id [WRITE]

- GET /projects/:id/milestones · POST /projects/:id/milestones [WRITE] · PATCH /milestones/:id [WRITE] · DELETE /milestones/:id [pmo/pm]

- GET /projects/:id/tasks · POST /projects/:id/tasks [WRITE] · POST /projects/:id/tasks/import [WRITE] (xlsx base64)

- GET /tasks/:id · PATCH /tasks/:id [WRITE] · DELETE /tasks/:id [pmo/pm]

- GET /tasks/:id/timelogs · POST /tasks/:id/timelogs [WRITE] · PATCH /tasks/:taskId/timelogs/:id [WRITE] · DELETE /tasks/:taskId/timelogs/:id [pmo/pm]

- GET /projects/:id/audit · GET /projects/:id/effort-burn · GET /projects/:id/burndown

- GET /projects/:id/critical-path (task CPM) · GET /projects/:id/schedule · GET /projects/:id/critical-path-stages (governance) · POST /projects/:id/critical-path/escalate [WRITE]

- POST /tasks/:id/dependencies [WRITE] · DELETE /tasks/:id/dependencies/:predId [pmo/pm]

- GET /projects/:id/nfa-status · POST /projects/:id/nfa-trigger [WRITE]

### 6.3.3	Project Stages (project_stages.ts) — WRITE

- GET /projects/:id/stages · POST /projects/:id/stages [WRITE]

- GET /project-stages/:id · PATCH /project-stages/:id [WRITE] · DELETE /project-stages/:id [pmo/pm]

- POST /projects/:id/stages/:stage/advance [WRITE] — the gate (only path that moves a stage)

- POST /projects/:id/stages/:stage/test-advance [WRITE] — dry-run gate check

### 6.3.4	Portfolios & Programs (portfolios.ts) — WRITE

- GET/POST /portfolios · GET/PATCH/DELETE /portfolios/:id · GET/POST /programs · GET/PATCH/DELETE /programs/:id

### 6.3.5	Workstreams (workstreams.ts)

- GET /projects/:id/workstreams · POST … [WRITE] · PATCH /workstreams/:id [WRITE] · DELETE /workstreams/:id [pmo/pm]

### 6.3.6	Resources / RACI (resources.ts)

- GET/POST /projects/:id/resource-allocations · PATCH/DELETE /resource-allocations/:id · GET/POST /projects/:id/raci · DELETE /raci/:id

### 6.3.7	Project Team (project_team.ts)

- GET /team-members · GET /projects/:id/team-members · POST … [WRITE] · PATCH/DELETE /team-members/:id · GET/POST /projects/:id/team-raci · DELETE /team-raci/:id

### 6.3.8	Budget (budget.ts)

- GET/POST /projects/:id/budget-lines · PATCH/DELETE /budget-lines/:id

### 6.3.9	Benefits (benefits.ts) — WRITE = pm/pmo/hod/finance

- GET /projects/:id/benefits-reviews · POST /projects/:id/benefits-reviews/init [WRITE] · PATCH /benefits-reviews/:id [WRITE] · GET /benefits-reviews/:id

### 6.3.10	Purchase Orders / Requisitions (purchase_orders.ts) — WRITE adds scm

- GET /prs · GET /prs/:id · POST /prs [WRITE] · POST /prs/:id/convert-to-po [WRITE] · POST /prs/:id/cancel [WRITE] · POST /prs/:id/refresh [WRITE] · DELETE /prs/:id

- GET /pos · GET /pos/:id · DELETE /pos/:id

### 6.3.11	NFAs (nfas.ts) — WRITE; DECIDE

- GET /nfas · GET /nfas/:id · POST /nfas [WRITE] · PATCH /nfas/:id [WRITE] · DELETE /nfas/:id · POST /nfas/:id/submit [WRITE] (route via DOA chain) · POST /nfas/:id/decide [DECIDE] · GET /nfas/:id/docx

### 6.3.12	PIFs (pifs.ts) — WRITE; DECIDE

- GET /pifs · GET /pifs/:id · POST /pifs [WRITE] · PATCH /pifs/:id [WRITE] · DELETE /pifs/:id · POST /pifs/:id/submit [WRITE] · POST /pifs/:id/decide [DECIDE] · POST /pifs/:id/convert-to-project [WRITE] · GET /pifs/inbox/:hodId

### 6.3.13	Approvals (approvals.ts) — DECIDE

- GET /approvals · GET /approvals/:id · POST /approvals/:id/decide [DECIDE] · GET /dashboard/pending-approvals

### 6.3.14	Change Requests & Baselines (change_requests.ts)

- GET /projects/:id/change-requests · GET /change-requests/:id · POST /projects/:id/change-requests [RAISE] · PATCH /change-requests/:id (decide logic inside)

- GET /projects/:id/baselines · POST /projects/:id/baselines [BASELINE] · PATCH /baselines/:id [BASELINE]

### 6.3.15	Scoring (scoring.ts) — SCORING = pmo/executive_director/chairman

- GET/POST /scoring-criteria · GET/PATCH/DELETE /scoring-criteria/:id · GET/POST /projects/:id/scores · PATCH/DELETE /project-scores/:id

### 6.3.16	Documents (documents.ts)

- GET /documents · GET /projects/:id/documents · POST /projects/:id/documents [WRITE] · GET /documents/:id · GET /documents/:id/share (mint share token) · PATCH /documents/:id [WRITE] · DELETE /documents/:id [pmo/pm] · GET /documents/:id/versions · POST /documents/:id/versions [WRITE]

- Public companion (documents-public.ts): GET /documents/:id/raw (wget, share-token) · PUT /documents/:id/raw (curl push new version)

### 6.3.17	Templates (templates.ts) — writes require requireRole("pmo")

- GET /templates · GET /templates/:id · POST/PATCH/DELETE /templates(/:id) · POST /templates/:id/tasks · PATCH/DELETE /template-tasks/:id · POST /templates/:id/milestones · PATCH/DELETE /template-milestones/:id · POST /templates/from-project/:projectId · POST /templates/import · POST /projects/from-template

- Public template files (template-files.ts): GET /storage/templates · GET /storage/templates/:phase/:file

### 6.3.18	Storage (storage.ts)

- POST /storage/uploads/request-url · GET /storage/public-objects/*filePath · GET /storage/objects/*path

- Local-FS PUT (local-uploads.ts): PUT /storage/local-uploads/:objectId

### 6.3.19	Meetings & MOM (meetings.ts) — WRITE

- GET /meetings · GET /projects/:id/meetings · POST /meetings [WRITE] · GET/PATCH/DELETE /meetings/:id · GET/POST /meetings/:id/items · PATCH/DELETE /meeting-items/:id

### 6.3.20	Notifications (notifications.ts)

- GET /notifications · PATCH /notifications/:id/read · POST /notifications/mark-all-read · POST /notifications

### 6.3.21	Nudges + Jobs (nudges.ts)

- GET /nudges · POST /nudges/:id/dismiss · POST /nudges/:id/acted-on · POST /nudges/bulk-dismiss

- jobsRouter: GET /jobs (scheduler status) · POST /jobs/run/:name (manual trigger)

### 6.3.22	Escalation Rules (escalation.ts)

- GET/POST /escalation-rules · PATCH/DELETE /escalation-rules/:id

### 6.3.23	Stage SLAs (stage_slas.ts)

- GET /stage-slas · PATCH /stage-slas/:stage [pmo]

### 6.3.24	Stage Escalation Policy (stage-escalation-policy.ts) — writes [pmo]

- GET /stage-escalation-policy · POST … · PATCH/DELETE /stage-escalation-policy/:id

### 6.3.25	DOA Matrix (doa_matrix.ts) — writes [pmo]

- GET /doa-matrix · GET /doa-matrix/preview · POST /doa-matrix · PATCH/DELETE /doa-matrix/:id

### 6.3.26	Role Directory (role-directory.ts) — writes [pmo]

- GET /role-directory · POST /role-directory · PATCH /role-directory/:role

### 6.3.27	Users / Employees (users.ts, employees.ts)

- GET /users/me · GET /users · GET /departments · POST /users · GET /users/:id · GET /employees/search · GET /employees/lookup

### 6.3.28	User Preferences (user_preferences.ts)

- GET /user-preferences · GET /user-preferences/default · POST /user-preferences · PATCH/DELETE /user-preferences/:id

### 6.3.29	Dashboard (dashboard.ts)

- GET /dashboard/ + summary, activity, gamification, portfolio-health, capacity-demand, milestone-achievers, stuck-approvals, delivery-stats, critical-path-portfolio, initiation-subgates, pending-approvals-by-person, overdue-actions-by-person, escalations-required, approval-sla-performance

### 6.3.30	Vendor Master (vendor_master.ts) — WRITE adds scm

- GET /vendors · POST /vendors [WRITE] · GET /vendors/:id · PATCH /vendors/:id [WRITE] · DELETE /vendors/:id

- POST /vendors/:id/segment · POST /vendors/:id/risk-status · POST /vendors/:id/documents · POST /vendors/:id/documents/:docId/verify · DELETE /vendors/:id/documents/:docId · POST /vendors/:id/qualifications · POST /vendors/:id/kpis · POST /vendors/:id/risk-events · POST /vendors/:id/risk-events/:eventId/resolve

- GET/POST /vendor-questionnaire-templates · PATCH …/:id

### 6.3.31	RFx (rfx.ts) — WRITE adds scm

- GET /rfx · POST /rfx [WRITE] · GET /rfx/:id · PATCH /rfx/:id [WRITE] · POST /rfx/:id/publish · POST /rfx/:id/cancel

- PUT /rfx/:id/questions · PUT /rfx/:id/dimensions · POST /rfx/:id/invitations

- POST /rfx/:id/envelopes/:kind/release-share (dual-role key share) · GET /rfx/:id/envelopes/:envelopeId/payload (decrypted bid after recombine)

- POST /rfx/:id/scores · GET /rfx/:id/scores · POST /rfx/:id/award · POST /rfx/:id/clarifications · POST /rfx/:id/clarifications/:clarId/answer · GET /rfx/:id/audit · POST /rfx/:id/surrogate-bid · DELETE /rfx/:id

### 6.3.32	Vendor Auth (vendor_auth.ts, public) — /api/auth/vendor/*

- POST /auth/vendor/send-verification-code · POST /auth/vendor/verify-email-code

### 6.3.33	Vendor Portal (vendor_portal.ts) — requireVendorAuth

- GET/PATCH /vendor/me · GET/POST /vendor/documents · GET /vendor/qualifications · GET /vendor/questionnaire-templates · POST /vendor/questionnaire-responses · GET /vendor/rfx · GET /vendor/rfx/:invitationId · POST /vendor/rfx/:invitationId/envelopes (submit sealed bid) · POST /vendor/rfx/:invitationId/clarifications

### 6.3.34	Admin

- /admin/integrations: GET / · GET /mcp-status · POST / · PUT/DELETE /:id · POST /:id/test

- /admin/roles (super-admin): GET / · GET /recent · PATCH /:employeeCode

### 6.3.35	Integrations

- Teams (integrations/teams.ts): POST /integrations/teams/import-meetings · POST /integrations/teams/:meetingId/sync-transcript · POST /integrations/teams/:meetingId/post-mom

- Jira (integrations/jira.ts): GET /integrations/jira/projects · GET /integrations/jira/projects/:key/components · POST /integrations/jira/import · POST /integrations/jira/export

Additional mounted routers outside the core enumeration: issues.ts, messages.ts, lessons.ts, charters.ts, work.ts, project-justifications.ts, leadership.ts.

## 6.4	6.4 Background jobs (src/jobs/)

lib/scheduler.ts is a dependency-free setInterval scheduler, opt-in via ENABLE_SCHEDULER=true. Per-job: 0–10 % boot jitter (cap 30 s), fires immediately + on interval, reentrancy guard (never overlaps itself), tracks lastRunAt/duration/lastError/consecutiveFailures (listJobs()); runJobNow(name) backs POST /api/jobs/run/:name.

| Job | Interval | What it does |
| --- | --- | --- |
| sap-sync.ts | 2 min | Polls SAP (mock or S/4HANA OData adapter) for every open PR/PO with a SAP number; updates local rows + lastSyncedAt; notifies the PM on a status transition. |
| escalation-evaluator.ts | 5 min | Evaluates active pmo_escalation_rules per project; fires one notification per notify_user_ids on breach; day-granular dedup. Triggers: rag_change, budget_overrun_pct, schedule_slip_days, risk_score, issue_open_days, stage_blocked_days. Email gated on autoEscalationEmailsEnabled(). |
| stage-escalation-ladder.ts | 60 min | Org-wide per-stage ladder. For each non-closed project, computes the governance critical path, finds the blocked/active stage, fires active pmo_stage_escalation_policy tiers past afterDays; resolves recipients via resolveRole, writes notifications + optional branded email + Teams channel email; logs a pmo_escalation_log row. 24h (project, stage, tier) dedup. |
| teams-sync.ts | 30 min | Pass 1: ingests recent Teams meetings into pmo_meetings. Pass 2: fetches transcripts, and (if LLM configured) extracts action_item/decision/information items into pmo_meeting_items, notifies the PM. |
| nudge-generator.ts | 15 min | NYRA-style adaptive nudges: heuristic scan of 6 signal kinds → dedupe via sha256 + (userId, llm_input_hash) unique index → one LLM call per user → persist pmo_nudges + mirror pmo_notifications. Caps: 25 users/tick, 6 signals/user. |

## 6.5	6.5 Library helpers (src/lib/)

- stage-gates.ts — authoritative lifecycle gate config (9 merged stages). Exports STAGE_GATES (per-stage blockingChecklistIds, requiredDocNames, advanceRoles), STAGE_META, STAGE_SUBGATES, STAGE_OWNER_ROLE, VENDOR_PATH, INTERNAL_SKIPPED_STAGES, applicableStages(type), prerequisiteFor, nextStageFor, and the read-only evaluateStageGate(...).

- gate-milestones.ts — the 7 governance gate-milestones each mapped to a stage; generateGateMilestones(projectId) (idempotent).

- critical-path.ts — lifecycle-STAGE governance critical path (computeStageCriticalPath): per-stage status/health, “waiting on” person, blocking reasons, next escalation rung, days pending/overdue.

- critical-path-cpm.ts — task-level CPM: Kahn topological sort + forward/backward pass → early/late start/finish, slack/float, isCritical; cycle-safe; wouldCreateDependencyCycle() guards new edges.

- critical-path-actions.ts — runCriticalPathAction(...) for manual escalate/remind; merges recipients, writes notifications + audit + pmo_escalation_log, and always emails (ignores the auto switch).

- rollup.ts — recomputeRollups(projectId): Subtask→Task→Milestone→Project progress_pct in one pass; only touches progress columns (never rag/gate/stage).

- notify.ts — multi-channel fan-out: in-app bell + branded email per recipient + one plain email to the project’s Teams channel address; notifyDetached(...) for fire-and-forget.

- mailer.ts — bridge to the shared backend mailer (backend/shared/mailer.js, sends as nyra@granulesindia.com): sendBrandedEmail, sendPlainEmail.

- escalation-email.ts — sendEscalationEmail (amber 🚩 banner) + autoEscalationEmailsEnabled() master switch.

- cxoActionSync.ts — PMO MoM → CXO Action Center mirror over the shared DB (raw pool SQL to avoid HTTP echo loops); cross-links pmo_meeting_items ↔ exec_action_items.

- masterDb.ts / vendorAuthDb.ts — lazy cached service-role Supabase clients (master employee DB; vendor-auth project).

- objectStorage.ts / localStorage.ts — GCS sidecar client (presigned URLs) + filesystem fallback under LOCAL_OBJECT_STORAGE_DIR (default ./uploads).

- envelopeCrypto.ts — RFx sealed-bid crypto: AES-256-GCM (12-byte IV, 16-byte authTag) + 2-of-2 XOR key split (share A = SCM, share B = PMO); sealJson/openJson; decryption needs both shares and the route enforces the closes_at deadline first.

- liveCharter.ts — extractDocText(doc) (PDF via pdf-parse / DOCX via mammoth / XLSX via xlsx; caps 15 MB / 12 000 chars) + buildStageMatrix (per-stage required-doc/checklist gap roll-up).

- templateDocuments.ts — seeds the 11 universal deliverable docs per project mapped to stages; blank files served by GET /api/storage/templates/:phase/:file.

- docShare.ts — stateless per-document share tokens = HMAC(PMO_DOC_PUSH_TOKEN, doc:<id>); constant-time validation; rotating the secret revokes all editor links.

- docBackfill.ts — document-driven stage backfill: extract text → LLM classifies (stage, doc name, satisfied checklist ids) → tick checklist + advance gates (audit-logged).

- approvalsAudit.ts — /admin/roles edits recorded as auto-approved pmo_role_change requests in the shared approval engine.

- mcpActivity.ts — in-memory tracker of PMO MCP “act-as” writes for the Connectors status card.

- cmdReports.ts — static leadership roster (CMD code 784 + 13 direct-report CXOs).

- nyraSql.ts — text-to-SQL guards for Ask NYRA (see §7.7).

- (There is no standalone lib/scoring.ts — project scoring lives in routes/scoring.ts; ranking via GET /api/projects/scoring-rank.)

# 7	7. Domain workflows

## 7.1	7.1 The PMO lifecycle (governance backbone)

SSOT: lib/stage-gates.ts (frontend mirror lib/lifecycle-config.ts). The enforcement model is 9 merged stages across 4 phases, with two project paths: vendor (all 9) and internal (skips vendor_selection + contract_po).

| Phase | Stage | Gate (blocking checklist, summarised) | Required docs | Advance roles |
| --- | --- | --- | --- | --- |
| Initiate | initiation | biz_just, scope_done, outcomes, budget_est, biz_req, it_review, biz_owner_approved, it_approved (+ BC & URS sub-gates) | URS Document, URS Review Sign-off | initiator, pmo, hod |
| Procure | vendor_selection (vendor only) | RFP created, vendors invited, deadline set, proposals analysed, negotiation complete, SCM + finance reviewed, vendor selected | RFP, Shortlist, Scorecards, Proposals, Negotiation Log, Finalized Commercials | scm, pmo, finance, hod |
|  | investment_authorization | charter / NFA / budget checklist | Project Charter, Charter Template, NFA Form, Budget Breakdown | pmo, hod, cfo, chairman |
|  | contract_po (vendor only) | contract uploaded, legal reviewed, compliance confirmed, legal sign-off, PR submitted, PO released | Vendor Contract, Legal Review Note, PR Form, PO Document | legal, pmo, finance, scm |
| Execute | design | kickoff / technical design / security review | MoM, Kickoff, Tech Design, Architecture, Security Review | pm, pmo, hod |
|  | build | dev env ready, status updated, impl plan, milestones defined, stakeholder sign-off, cutover plan | Build Specs, Status Report, Impl Plan, Cutover Plan | pm, pmo |
| Release & Close | uat | uat_plan_approved, test_cases_executed, critical_defects_closed, uat_signed (+ zero open uat_defect issues) | UAT Test Plan, Sign-off, Defect Log | pm, hod |
|  | go_live | go-live date frozen, training uploaded, stakeholders notified | Go Live Checklist, Training Materials, Comms Plan | pm, pmo |
|  | closure | CSAT, doc handover, deliverables signed, support transitioned, lessons_learned_done, closure report, final financials | Closure Report, CSAT, Handover | pm, pmo, chairman |

Gate enforcement: advancing a stage is only possible via POST /api/projects/:id/stages/:stage/advance. Server-side it checks: prerequisite stage complete → role ∈ advanceRoles → all blocking checklist items ticked (state in pmo_project_stages.notes.__checklist) → required docs uploaded (matched by name) → sub-gate approvals (BC, then URS dual approval) → UAT defects closed. evaluateStageGate() is the non-mutating evaluator reused by the critical-path display. STAGE_OWNER_ROLE gives each stage a default escalation owner (e.g. investment_authorization → cfo, uat → qa_lead). gate-milestones.ts auto-creates 7 gate milestones tagged by stage.

Taxonomy note: the backend gates 9 merged stages; the product/marketing docs and document-templates/README.md describe a 13-stage / 3-phase taxonomy (Plan / Execute / Close) to which the 15 mandatory templates are mapped. The 15 templates are not yet wired into gate config (requiredDocNames).

## 7.2	7.2 Charter + e-NFA flow

The Charter and the e-NFA (Note For Approval) are merged into one pmo_charters row (legacy pmo_nfas kept read-only). The charter carries both the narrative/business-case sections and the absorbed NFA fields (subject, background, requirement line-items, costing, recommendation, signatory grid). The 2-step AI draft is the charter wizard: step 1 structured fields, step 2 narrative + user-defined customFields, generated/improved via routes/ai.ts. On /submit, the DOA resolver computes the signatory chain and mirrors one pmo_approvals row per role. Charter approvals flow parallel review → SCM → Chairman → Finance → PMO.

## 7.3	7.3 Demand → PIF → RFx → Vendor → PO

- Demand intake → PIF (pmo_pifs): problem, solution, sponsor + HOD, outcomes, metrics, ballpark capex/opex. HOD reviews (draft → submitted → under_review → approved/rejected).

- PIF → Project: /convert-to-project spawns a real project (+ optional charter shell), setting convertedProjectId.

- Vendor selection / RFx (vendor path): create pmo_rfx_events (RFI/RFP/RFQ/e-auction) → invite vendors (tokenized pmo_rfx_invitations) → vendors submit sealed AES-256-GCM envelopes on the OTP portal → after the deadline, the 2-of-2 XOR-shared key is released by two officers to open envelopes → blind-graded scoring (pmo_rfx_scores, grader aliases); the commercial envelope only unlocks once the tech score crosses evaluationThresholdPct (default 60) → clarifications → award (pmo_rfx_awards, split-award capable) → full pmo_rfx_audit.

- Contract & PO: approved selection → pmo_purchase_requisitions pushed to SAP → /convert-to-po → pmo_purchase_orders; sap-sync polls status.

- Vendor master: pmo_vendor_master is the source of truth (segment, riskStatus rolled from pmo_vendor_risk_events, KPIs, qualifications, compliance docs with expiry).

## 7.4	7.4 DOA matrix (Delegation of Authority)

pmo_doa_matrix is a lookup keyed by (entity, category, kind, amount band), each dimension wildcard-able with *. Resolver lib/doa-resolver.ts filters active rows whose amount ∈ [minInr, maxInr) and matches entity/category/kind exactly or via *, scores specificity, and returns the ordered approverRoles. Charter /submit inserts one pmo_approvals row per role. Seeded placeholder bands (org-wide */*/*):

- ₹0 – ₹50 L → [hod]

- ₹50 L – ₹5 Cr → [hod, cfo]

- Above ₹5 Cr → [hod, cfo, executive_director, chairman]

## 7.5	7.5 Scoring, SLAs, escalation, nudges

- Scoring: pmo_scoring_criteria (weighted) × pmo_project_scores → scoringTotal, for prioritization. Configured at /admin/scoring.

- SLAs: pmo_stage_slas (target days per stage) drives “days overdue”; pmo_approvals.slaHours (48), pmo_change_requests.slaHours (72).

- Two escalation engines (both dormant unless ENABLE_SCHEDULER=true):

  - Condition rules — pmo_escalation_rules + escalation-evaluator (5 min). In-app only, deduped per rule/day. The /automations “When…then…” gallery writes real rows here (no parallel engine).

  - Stage ladder — pmo_stage_escalation_policy + stage-escalation-ladder (hourly). Tiered rungs (afterDays from stage entry) fire remind/escalate to targetRole (resolved via role-resolver.ts + pmo_role_directory), logged to pmo_escalation_log. Auto emails gated by AUTO_ESCALATION_EMAILS; manual buttons always email.

- Nudges: nudge-generator (15 min) writes LLM-composed pmo_nudges + mirrored notifications; lifecycle active/dismissed/acted_on/expired.

## 7.6	7.6 Documents & templates

pmo_documents + pmo_document_versions: versioned files in object storage (GCS / local fallback), per-stage tagging, approval workflow, accessLevel, and an AI summary cache feeding the Live Project Charter. Gate “required docs” are matched by exact name against pmo_documents.name. The 15 mandatory templates live in document-templates/{Plan,Execute,Close}/. Tech-team push via PUT /api/documents/:id/raw with PMO_DOC_PUSH_TOKEN; public read via GET /api/documents/:id/raw with a share token.

## 7.7	7.7 Ask NYRA (embedded AI analyst)

A conversational, read-only analyst in the header (AskNyra.tsx → POST /api/ai/ask). It is an agentic text-to-SQL loop (llmWithTools, maxTurns 5) with a single tool query_database. lib/nyraSql.ts enforces three gates on every LLM-authored query:

- assertReadOnlySelect — single statement, SELECT/WITH only, no DML/DDL/;, blocks a WRITE_KEYWORDS regex (incl. pg_sleep, pg_read_file, dblink), auto-appends LIMIT 1000.

- assertPmoTablesOnly — every FROM/JOIN base table must start with pmo_ (CTEs exempt) — hard-walling off recruit/HR PII in the shared DB.

- Authenticated PMO users only; runReadOnly runs in a READ ONLY tx with statement_timeout=12000 and always ROLLBACKs.

getNyraSchemaDocs() introspects information_schema.columns for ~18 exposed pmo_* tables (5-min cache) and feeds the model human-readable schema + relationships + enum spellings. Each answer surfaces the executed SQL + rows in a “queries run” panel for auditability.

## 7.8	7.8 Other AI endpoints (routes/ai.ts)

All AI routes go through the single @workspace/llm helper. Model: provider anthropic, default claude-sonnet-4-6. GET /api/ai/status reports {configured, provider, model}. Feature endpoints (POST under /api/ai): improve-text (Rephrase); charter rewrite-brd / risk-suggestions / draft-fields / extract-fields / draft-template / draft-narrative; nfa/draft* / nfa/extract-fields; pif/draft-from-idea / pif/critique; demand/draft-idea / demand/draft; urs/draft; rfp/draft-sections / rfp/draft-annexure; rfx/draft-questions / rfx/award-scenarios; vendor score / suggest-list / suggest-dimensions / score-matrix / insights / extract-document / risk-summary; projects/:id/budget-insights / dashboard-summary / audit-rca; meetings/:id/extract-action-items; lessons-learned/search; kickoff/agenda; Live Charter GET/POST /projects/:id/live-charter(/refresh); POST /projects/:id/backfill-from-docs.

# 8	8. Data model

All pmo_* tables live in the Recruit Supabase DB (~63 tables across the schema files). Most FK-style columns are bare integer (no DB-level FK); some identity columns are master-DB UUID strings; many date columns are text “YYYY-MM-DD”.

## 8.1	8.1 Core project structure

| Table | Purpose |
| --- | --- |
| pmo_portfolios | Top-level grouping (id, name, ownerId). |
| pmo_programs | Program under a portfolio (portfolioId, ownerId). |
| pmo_projects | The project (central entity): charterId, portfolio/programId, status, priority, stage, projectType (vendor¦internal — drives whether the 2 procurement stages apply), category (CAPEX/NPX/CIP/IT), ragStatus (human), budgets, budgetThresholdPct, scoringTotal, siteRegion, function, projectManagerId, teamsChannelEmail, start/endDate, progress, jiraKey. |
| pmo_charters | Merged Charter + e-NFA: scope, deliverables, business benefits, narrative sections, investment summary (capex/opex/roi/payback drive DOA), absorbed NFA fields, signatories (resolved from DOA matrix), roadmap/governance JSONB. |
| pmo_nfas | Legacy standalone NFA (read-only back-compat). |
| pmo_live_charters | Cached AI-assembled read-only “Live Project Charter” (one per project): narrative markdown + per-stage matrix + docDigest + stale flag. |
| pmo_pifs | Project Initiation Form (pre-charter demand): problem, solution, sponsor/HOD, outcomes/metrics/risks JSONB, est capex/opex, status, convertedProjectId. |
| pmo_project_justifications | Owner justification when a project goes delayed/off-track. |
| pmo_squad_members | Charter team membership (role). |
| pmo_workstreams | Optional self-referential sub-grouping. |

## 8.2	8.2 Work management (Monday layer)

| Table | Purpose |
| --- | --- |
| pmo_milestones | Milestone / gate marker: stage, progressPct (rolled), rag (human), readinessChecklist, gateDecision, scheduleVarianceDays, jiraKey. |
| pmo_tasks | Task and subtask (self-ref parentTaskId): milestoneId, assigneeId, cftOwner/dept, stage, progressPct, dates + endDateHistory, effort hours, predecessorIds + crossProjectPredecessors, isCritical, jiraKey/Component. |
| pmo_raci_matrix | Per-task/workstream RASCI (raciType R/A/S/C/I). |
| pmo_resource_allocations | Person × workstream allocation % + skill + dates. |
| pmo_timelogs | Time entries against a task. |
| pmo_messages | Task/milestone comment threads (attachments, taggedUserIds, threadParentId). |
| pmo_project_templates | Reusable project blueprint (soft-delete via isActive). |
| pmo_template_tasks | Task blueprint (self-ref, offset-based dates, predecessorOffsets). |
| pmo_template_milestones | Milestone blueprint. |
| pmo_project_team_members | Project Team roster (internal userId / external name+org+email+kind, approval state). |
| pmo_project_team_raci | Project-level RACI (member × deliverable). |

## 8.3	8.3 Lifecycle, stages & governance

| Table | Purpose |
| --- | --- |
| pmo_project_stages | One row per stage per project: status, enteredAt/completedAt, notes JSON (__checklist map + sub-gate flags __bc_approved, __urs_biz_approved, __urs_it_approved). |
| pmo_stage_slas | Admin per-stage target duration (drives days-overdue). |
| pmo_approvals | Approval steps for charters/gates: approverRole, stage, status, slaHours (48), dueAt, breachedAt. |
| pmo_doa_matrix | Delegation-of-Authority bands: entity/category/kind (default *), minInr/maxInr, ordered approverRoles. |
| pmo_baselines | Gate snapshot; once locked only a CR changes baselined values. |
| pmo_change_requests | Formal change control: crNumber, scheduleImpactDays, budgetImpact, status, slaHours (72), baseline/proposed snapshots. |
| pmo_risks | Risk register (charter-scoped): impact, likelihood, mitigation, rag. |
| pmo_issues | Issue register (also UAT defects via dependencyType=uat_defect). |
| pmo_benefits_reviews | Post-go-live benefits (+3/+6/+12 mo): projected vs actual, realizationPct. |
| pmo_lessons_learned | Cross-project knowledge (closure gate). |
| pmo_activity | Append-only audit log. |

## 8.4	8.4 Documents

| Table | Purpose |
| --- | --- |
| pmo_documents | Project documents (gate required-docs matched by name): stage, version, approvalStatus, accessLevel, tags, AI summary cache. |
| pmo_document_versions | Version history. |

## 8.5	8.5 Escalations & notifications

| Table | Purpose |
| --- | --- |
| pmo_escalation_rules | Per-project condition rules (triggerType, thresholdValue, notifyUserIds). |
| pmo_stage_escalation_policy | Org-wide tiered ladder per stage (subGateKey, tier, afterDays, action, targetRole). |
| pmo_escalation_log | Append-only fired-escalation audit + dedupe (source ladder¦manual). |
| pmo_role_directory | Role → person/email map (unique role). |
| pmo_role_overrides | Per-employee PMO role override (in Recruit DB, since master employee_auth.pmo_role only allows admin). |
| pmo_notifications | In-app notifications. |
| pmo_nudges | LLM-composed proactive nudges (llmInputHash dedupe, status active/dismissed/acted_on/expired). |

## 8.6	8.6 Procurement / RFx / vendors

| Table | Purpose |
| --- | --- |
| pmo_vendor_master | First-class supplier identity: GST/PAN, sapVendorCode, segment (strategic…blocked), riskStatus, authUserId. |
| pmo_vendors | Charter-scoped vendor candidate (proposedPrice, isSelected, masterVendorId). |
| pmo_vendor_documents | Compliance docs + verification trail (kind, verifiedBy/At, expiresAt). |
| pmo_vendor_qualifications | Per (vendor, category, region, BU) qualification matrix. |
| pmo_vendor_questionnaire_templates / _responses | Vendor self-assessments. |
| pmo_vendor_kpis | Per-period scorecard (onTime/quality/responsiveness, compositeScore). |
| pmo_vendor_risk_events | Append-only risk signal feed (source, severity). |
| pmo_purchase_requisitions | PR to SAP (sapPrNumber, lineItems, sapStatus, lastSyncedAt). |
| pmo_purchase_orders | PO from approved PR (sapPoNumber, deliveryDate, sapStatus). |

RFx subsystem (pmo_rfx_*, sealed-bid): pmo_rfx_events (type, status, opens/closesAt, auctionMode, evaluationThresholdPct, blindGrading), pmo_rfx_invitations (inviteToken), pmo_rfx_questions, pmo_rfx_envelope_keys (2-of-2 XOR key shares A/B), pmo_rfx_envelopes (AES-GCM sealedPayload/iv/authTag, labelAlias), pmo_rfx_envelope_files, pmo_rfx_scoring_dimensions, pmo_rfx_scores (graderAlias), pmo_rfx_clarifications, pmo_rfx_awards (split-award sharePct), pmo_rfx_audit.

## 8.7	8.7 Reporting / scoring / meetings / config

| Table | Purpose |
| --- | --- |
| pmo_scoring_criteria | Prioritization criteria (weightPct). |
| pmo_project_scores | Project × criterion weighted score. |
| pmo_budget_lines | Budget baseline vs forecast vs actual + variance. |
| pmo_meetings | Meetings/MoM (Teams-synced): type, isCxoContainer, teamsMeetingId, transcript, momPosted. |
| pmo_meeting_items | Action items/decisions (category, execActionItemId CXO cross-link). |
| pmo_users | Local app user (auto-provisioned from Master DB on first login; FK target for created_by/owner). |
| pmo_user_preferences | Per-user saved views (scope, config JSON, isDefault). |
| pmo_mcp_integrations | External connector registry (jira implemented; github/streamliner placeholders). |

# 9	9. Integrations

| Integration | Where | Notes |
| --- | --- | --- |
| Jira | routes/integrations/jira.ts, pmo_mcp_integrations | Two-way task import/export (verified: MYG → 264 tasks). Epics import to milestones; export writes to live Jira (UI-triggered). |
| Teams | routes/integrations/teams.ts + jobs/teams-sync.ts (30 min) | Meeting MoM ingest + transcript → LLM action-item extraction. Posts MoM to channel via the SMTP email-to-channel path (teamsChannelEmail). |
| SAP | integrations/sap/ + jobs/sap-sync.ts (2 min) | PR/PO status sync; mock adapter by default (SAP_MODE=real switches to S/4HANA OData). |
| PMO MCP | X-PMO-Service-Token act-as auth | External automation pushes PM updates with full Jira/Confluence-parity tools; gated by PMO_MCP_TOKEN + PMO_MCP_ACTORS. |
| CXO Action Centre | lib/cxoActionSync.ts | PMO MoM action items mirror into exec_action_items (and back) over the shared DB. |

# 10	10. Cheat sheet

| Need | Where |
| --- | --- |
| Add a lifecycle stage / change a gate | lib/stage-gates.ts (+ mirror lib/lifecycle-config.ts) |
| Change rollup math | lib/rollup.ts |
| Task critical path / dependencies | lib/critical-path-cpm.ts |
| Governance critical path | lib/critical-path.ts |
| Escalation behaviour | jobs/escalation-evaluator.ts, jobs/stage-escalation-ladder.ts, lib/role-resolver.ts |
| RBAC roles | lib/derivePmoRole.ts, lib/guard.ts, middlewares/requireAuth.ts |
| DOA approver chain | lib/doa-resolver.ts + scripts/add-doa-matrix-and-merge-charter-nfa.sql |
| NYRA guards | lib/nyraSql.ts |
| RFx sealed-bid crypto | lib/envelopeCrypto.ts |
| WBS tree / board kit | components/wbs-tree.tsx, components/monday/ |
| Turn on automations/escalations | ENABLE_SCHEDULER=true (+ AUTO_ESCALATION_EMAILS=on) + assign people in /admin/role-directory |
| Schema source of truth | lib/db/src/schema/*.ts |
| Apply DB changes | hand-written SQL in scripts/ (never drizzle-kit push) |

## 10.1	10.1 Known gaps / inconsistencies

- Stage-count drift: backend gates 9 merged stages; product docs + template README describe a 13-stage / 3-phase taxonomy. The 15 mandatory templates are mapped to the 13-stage keys and not yet wired into gate requiredDocNames.

- Legacy role read: a few endpoints (project_stages, scoring, storage, dashboard) still read the dev session.simulatedRole; the POST /session/role simulator is dev-only (403 in prod).

- Two RACI tables: per-task pmo_raci_matrix vs project-level pmo_project_team_raci.

- Charter/NFA merge: new writes → pmo_charters; pmo_nfas is legacy read-only.

- Vendor auth DB currently reuses the Recruit/candidate Supabase project as a documented fallback.