## Project Template
S.No | Milestone Name | Task List Name | Parent Task ID | Parent Task Name | Task ID | Task Name | Owner | Dependency status | Critical Task | Predecessors | Successors
| Project initiation | Project initiation | - |  | VE3-T1 | Project introduction form (PIF)
| Project initiation | Project initiation | - |  | VE3-T2 | Agreement (in case of Co-Development )
| Project initiation | Project initiation | - |  | VE3-T3 | Project kickoff
| Full kit for Product Development | Fullkitting | - |  | VE3-T4 | Product Development Strategy Note (PDSN)
| Full kit for Product Development | Fullkitting | VE3-T4 | Product Development Strategy Note (PDSN) | VE3-T5 | IP CLSF Report
| Full kit for Product Development | Fullkitting | VE3-T4 | Product Development Strategy Note (PDSN) | VE3-T6 | Regulatory strategy note
| Full kit for Product Development | Fullkitting | VE3-T4 | Product Development Strategy Note (PDSN) | VE3-T7 | Marketing Requirements (Pack mode & special interest based on market demand)
| Full kit for Product Development | Fullkitting | VE3-T4 | Product Development Strategy Note (PDSN) | VE3-T8 | PDSN Preparation
| Full kit for Product Development | Fullkitting | - |  | VE3-T9 | Licenses - R&D Centre
| Full kit for Product Development | Fullkitting | VE3-T9 | Licenses - R&D Centre | VE3-T10 | NOC for API (if applicable) - R&D Centre
| Full kit for Product Development | Fullkitting | VE3-T9 | Licenses - R&D Centre | VE3-T11 | NOC for Finished product (if applicable) - R&D Centre
| Full kit for Product Development | Fullkitting | VE3-T9 | Licenses - R&D Centre | VE3-T12 | Test license availability - R&D Centre
| Full kit for Product Development | Fullkitting | VE3-T9 | Licenses - R&D Centre | VE3-T13 | API Import license (if required) - R&D Centre
| Full kit for Product Development | Fullkitting | - |  | VE3-T14 | Licenses - GMP Facility
| Full kit for Product Development | Fullkitting | VE3-T14 | Licenses - GMP Facility | VE3-T15 | NOC for API (if applicable) - GMP Facility
| Full kit for Product Development | Fullkitting | VE3-T14 | Licenses - GMP Facility | VE3-T16 | NOC for Finished product (if applicable) - GMP Facility
| Full kit for Product Development | Fullkitting | VE3-T14 | Licenses - GMP Facility | VE3-T17 | Test license availability - GMP Facility
| Full kit for Product Development | Fullkitting | VE3-T14 | Licenses - GMP Facility | VE3-T18 | API import license (if required) - GMP Facility
| Full kit for Product Development | Fullkitting | - |  | VE3-T19 | Licenses - RLD
| Full kit for Product Development | Fullkitting | VE3-T19 | Licenses - RLD | VE3-T20 | RLD - NOC (if Applicable)
| Full kit for Product Development | Fullkitting | VE3-T19 | Licenses - RLD | VE3-T21 | RLD Import license
| Full kit for Product Development | Fullkitting | - |  | VE3-T22 | IH API for Development
| Full kit for Product Development | Fullkitting | VE3-T22 | IH API for Development | VE3-T23 | IH API Requirement - Note For approval
| Full kit for Product Development | Fullkitting | VE3-T22 | IH API for Development | VE3-T24 | IH API receipt for development
| Full kit for Product Development | Fullkitting | VE3-T22 | IH API for Development | VE3-T25 | IH API related docs (Characterization data/ Impurities declaration etc)
| Full kit for Product Development | Fullkitting | VE3-T22 | IH API for Development | VE3-T26 | IH API Techpack / O DMF availability
| Full kit for Product Development | Fullkitting | - |  | VE3-T27 | OS API for Development
| Full kit for Product Development | Fullkitting | VE3-T27 | OS API for Development | VE3-T28 | OS API Requirement - Note For approval
| Full kit for Product Development | Fullkitting | VE3-T27 | OS API for Development | VE3-T29 | OS API receipt for development
| Full kit for Product Development | Fullkitting | VE3-T27 | OS API for Development | VE3-T30 | OS API related docs (Characterization data/ Impurities declaration etc)
| Full kit for Product Development | Fullkitting | VE3-T27 | OS API for Development | VE3-T31 | OS API Techpack / O DMF availability
| Full kit for Product Development | Fullkitting | - |  | VE3-T32 | RLD availability for Development
| Full kit for Product Development | Fullkitting | VE3-T32 | RLD availability for Development | VE3-T33 | RLD Requirement - Note For approval
| Full kit for Product Development | Fullkitting | VE3-T32 | RLD availability for Development | VE3-T34 | RLD PR / PO
| Full kit for Product Development | Fullkitting | VE3-T32 | RLD availability for Development | VE3-T35 | RLD Receipt
| Full kit for Product Development | Fullkitting | - |  | VE3-T36 | Excipients availability for Development
| Full kit for Product Development | Fullkitting | VE3-T36 | Excipients availability for Development | VE3-T37 | New excipients request (if any) to SCM
| Full kit for Product Development | Fullkitting | VE3-T36 | Excipients availability for Development | VE3-T38 | Sample quantity arrangement (along with Docs)
| Full kit for Product Development | Fullkitting | VE3-T36 | Excipients availability for Development | VE3-T39 | New excipients PR (If req)
| Full kit for Product Development | Fullkitting | VE3-T36 | Excipients availability for Development | VE3-T40 | New excipients PO to receipt
| Full kit for Product Development | Fullkitting | - |  | VE3-T41 | Packing material availability for Development
| Full kit for Product Development | Fullkitting | - |  | VE3-T42 | Analytical requirements readiness
| Full kit for Product Development | Fullkitting | - |  | VE3-T43 | Phase gate 1 clearance
| Development | Formulation Development | - |  | VE3-T44 | Prototype development
| Development | Formulation Development | VE3-T44 | Prototype development | VE3-T45 | RLD characterization
| Development | Formulation Development | VE3-T44 | Prototype development | VE3-T46 | Tooling/change parts for development
| Development | Formulation Development | VE3-T44 | Prototype development | VE3-T47 | Packing configuration finalization
| Development | Formulation Development | VE3-T44 | Prototype development | VE3-T48 | Preformulation studies (Drug Excipient compatibility studies, PXRD etc.)
| Development | Formulation Development | VE3-T44 | Prototype development | VE3-T49 | Risk assessment of formulation (QTPP, CQA & CMAs but not limited to)
| Development | Formulation Development | VE3-T44 | Prototype development | VE3-T50 | Risk assessment of process (CPP but not limited to)
| Development | Formulation Development | VE3-T44 | Prototype development | VE3-T51 | Risk assessment of packing (CMA but not limited to)
| Development | Formulation Development | VE3-T44 | Prototype development | VE3-T52 | Dissolution mapping in release medium
| Development | Formulation Development | VE3-T44 | Prototype development | VE3-T53 | Dissolution mapping in multimedia
| Development | Formulation Development | VE3-T44 | Prototype development | VE3-T54 | Dissolution mapping in biorelevant dissolution conditions (if required)
| Development | Formulation Development | VE3-T44 | Prototype development | VE3-T55 | Stress stability (accelerated conditions like heat, humidity, open exposure etc.)
| Development | Formulation Development | - |  | VE3-T56 | Formulation finalization
| Development | Formulation Development | VE3-T56 | Formulation finalization | VE3-T57 | Formulation optimization
| Development | Formulation Development | VE3-T56 | Formulation finalization | VE3-T58 | Process optimization
| Development | Formulation Development | VE3-T56 | Formulation finalization | VE3-T59 | Discriminatory dissolution trials
| Development | Formulation Development | - |  | VE3-T60 | API availability for Pilot BE batches
| Development | Formulation Development | VE3-T60 | API availability for Pilot BE batches | VE3-T61 | IH API for pilot BE Batches
| Development | Formulation Development | VE3-T60 | API availability for Pilot BE batches | VE3-T62 | IH API Declarations (EI, RSL, GTI, Benzene content, Stab data etc)
| Development | Formulation Development | VE3-T60 | API availability for Pilot BE batches | VE3-T63 | OS API PR for pilot BE Batches
| Development | Formulation Development | VE3-T60 | API availability for Pilot BE batches | VE3-T64 | OS API PO to receipt for pilot BE Batches
| Development | Formulation Development | - |  | VE3-T65 | Excipient for Pilot BE batches
| Development | Formulation Development | VE3-T65 | Excipient for Pilot BE batches | VE3-T66 | BOM Finalization
| Development | Formulation Development | VE3-T65 | Excipient for Pilot BE batches | VE3-T67 | PR Release
| Development | Formulation Development | VE3-T65 | Excipient for Pilot BE batches | VE3-T68 | PO Release & RM receipt
| Development | Formulation Development | - |  | VE3-T69 | Pilot BE - Preparation
| Development | Formulation Development | VE3-T69 | Pilot BE - Preparation | VE3-T70 | BE CRO Selection & Qualification (if required)
| Development | Formulation Development | VE3-T69 | Pilot BE - Preparation | VE3-T71 | RLD availability for Pilot BE study
| Development | Formulation Development | VE3-T69 | Pilot BE - Preparation | VE3-T72 | Pilot BE Study Protocols readiness
| Development | Formulation Development | VE3-T69 | Pilot BE - Preparation | VE3-T73 | BENOC Document submission
| Development | Formulation Development | VE3-T69 | Pilot BE - Preparation | VE3-T74 | Test license/BENOC for Pilot BE
| Development | Formulation Development | - |  | VE3-T75 | Risk assessment
| Development | Formulation Development | VE3-T75 | Risk assessment | VE3-T76 | Residual solvents risk assessment report
| Development | Formulation Development | VE3-T75 | Risk assessment | VE3-T77 | Genotoxic impurities risk assessment report
| Development | Formulation Development | VE3-T75 | Risk assessment | VE3-T78 | Elemental impurities risk assessment report
| Development | Formulation Development | VE3-T75 | Risk assessment | VE3-T79 | Nitrosamine risk assessment report
| Development | Formulation Development | VE3-T75 | Risk assessment | VE3-T80 | Iron content assessment report
| Development | Formulation Development | - |  | VE3-T81 | Phase gate 2 clearance
| Development | Formulation Development | - |  | VE3-T82 | 1M stability of prototype formulation
| Development | Formulation Development | - |  | VE3-T83 | 2M stability of prototype formulation
| Development | Formulation Development | - |  | VE3-T84 | 3M stability of prototype formulation
| Development | Analytical development | - |  | VE3-T85 | Residue method development
| Development | Analytical development | VE3-T85 | Residue method development | VE3-T86 | Residue method IOC & Sample submission
| Development | Analytical development | VE3-T85 | Residue method development | VE3-T87 | Residue/cleaning method development
| Development | Analytical development | VE3-T85 | Residue method development | VE3-T88 | Residue/cleaning method fullkit to QC
| Development | Analytical development | VE3-T85 | Residue method development | VE3-T89 | AMV of Residue/cleaning method at QC
| Development | Analytical development | - |  | VE3-T90 | Analytical method development by QbD
| Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T91 | AMD Sample submission with Spec IOC
| Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T92 | Analytical method development in-process
| Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T93 | Analytical method development finished product
| Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T94 | Forced degradation studies
| Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T95 | Solubility profile data generation
| Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T96 | Dissolution method development-Release medium
| Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T97 | Dissolution method development-Multi media
| Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T98 | Dissolution method development-Bio-relevant (if required)
| Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T99 | IP & FP specification finalization & justification
| Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T100 | AMV Sample submission
| Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T101 | AMV Sample COA generation & Fullkit to QC
| Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T102 | Elemental impurities AMD - IOC & Sample submission
| Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T103 | Elemental impurities AMD & full kit to QC (if required)
| Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T104 | Nitroso impurities AMD - IOC & Sample submission
| Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T105 | Nitroso impurities AMD & full kit to QC (if required)
| Development | Analytical development | - |  | VE3-T106 | New Raw materials - Analytical method
| Development | Analytical development | VE3-T106 | New Raw materials - Analytical method | VE3-T107 | API submission for Method feasibility with IOC
| Development | Analytical development | VE3-T106 | New Raw materials - Analytical method | VE3-T108 | API Analytical method feasibility testing & ful kit to QC (in-case of outsourced APIs)
| Development | Analytical development | VE3-T106 | New Raw materials - Analytical method | VE3-T109 | API specification finalization & justification (in-case of outsourced APIs)
| Development | Analytical development | VE3-T106 | New Raw materials - Analytical method | VE3-T110 | New Raw materials - IOC & Sample submission to FARD
| Development | Analytical development | VE3-T106 | New Raw materials - Analytical method | VE3-T111 | New Raw materials - Feasibility testing
| Development | Analytical development | VE3-T106 | New Raw materials - Analytical method | VE3-T112 | New Raw materials - Full kit to QC
| Development | Analytical development | VE3-T106 | New Raw materials - Analytical method | VE3-T113 | Method equivalency testing (if any)
| Pilot BE studies | Pilot BE | - |  | VE3-T114 | L1 Clearances
| Pilot BE studies | Pilot BE | VE3-T114 | L1 Clearances | VE3-T115 | IIG Clearance (L1)
| Pilot BE studies | Pilot BE | VE3-T114 | L1 Clearances | VE3-T116 | IPR Clearance (L1)
| Pilot BE studies | Pilot BE | VE3-T114 | L1 Clearances | VE3-T117 | Trade dress / Trademark Clearance (L1)
| Pilot BE studies | Pilot BE | VE3-T114 | L1 Clearances | VE3-T118 | Size & shape Clearance (L1)
| Pilot BE studies | Pilot BE | VE3-T114 | L1 Clearances | VE3-T119 | Product Costing clearance - Cost/pill (L1)
| Pilot BE studies | Pilot BE | - |  | VE3-T120 | Pilot BE IPs readiness
| Pilot BE studies | Pilot BE | VE3-T120 | Pilot BE IPs readiness | VE3-T121 | Pilot BE batch(es) manufacturing
| Pilot BE studies | Pilot BE | VE3-T120 | Pilot BE IPs readiness | VE3-T122 | Pilot BE Test batch(es) analysis (CoA, release and multimedia dissolutions)
| Pilot BE studies | Pilot BE | VE3-T120 | Pilot BE IPs readiness | VE3-T123 | Pilot BE RLD analysis (CoA, release and multimedia dissolutions)
| Pilot BE studies | Pilot BE | VE3-T120 | Pilot BE IPs readiness | VE3-T124 | Note for Approval for Pilot BE study (Technical)
| Pilot BE studies | Pilot BE | VE3-T120 | Pilot BE IPs readiness | VE3-T125 | Note for Approval for Pilot BE study - Budget/PR / PO Release
| Pilot BE studies | Pilot BE | VE3-T120 | Pilot BE IPs readiness | VE3-T126 | IPs shipment to CRO
| Pilot BE studies | Pilot BE | - |  | VE3-T127 | Phase gate 3 clearance
| Pilot BE studies | Pilot BE | - |  | VE3-T128 | Pilot BE Study(ies)
| Pilot BE studies | Pilot BE | VE3-T128 | Pilot BE Study(ies) | VE3-T129 | Fasting pilot BE study (Clinic Start - End)
| Pilot BE studies | Pilot BE | VE3-T128 | Pilot BE Study(ies) | VE3-T130 | Fasting study results
| Pilot BE studies | Pilot BE | VE3-T128 | Pilot BE Study(ies) | VE3-T131 | Fed pilot BE study (Clinic Start - End)
| Pilot BE studies | Pilot BE | VE3-T128 | Pilot BE Study(ies) | VE3-T132 | Fed study results
| Pilot BE studies | Pilot BE | VE3-T128 | Pilot BE Study(ies) | VE3-T133 | Any other studies
| Pilot BE studies | Pilot BE | - |  | VE3-T134 | Material procurement for scale up
| Pilot BE studies | Pilot BE | VE3-T134 | Material procurement for scale up | VE3-T135 | BOM Submission for SU
| Pilot BE studies | Pilot BE | VE3-T134 | Material procurement for scale up | VE3-T136 | API PR
| Pilot BE studies | Pilot BE | VE3-T134 | Material procurement for scale up | VE3-T137 | API PO to receipt
| Pilot BE studies | Pilot BE | VE3-T134 | Material procurement for scale up | VE3-T138 | RM PR
| Pilot BE studies | Pilot BE | VE3-T134 | Material procurement for scale up | VE3-T139 | RM PO to receipt
| Pilot BE studies | Pilot BE | VE3-T134 | Material procurement for scale up | VE3-T140 | PM PR
| Pilot BE studies | Pilot BE | VE3-T134 | Material procurement for scale up | VE3-T141 | PM PO to receipt
| Pilot BE studies | Pilot BE | - |  | VE3-T142 | Tooling/change parts for SU/EB
| Pilot BE studies | Pilot BE | VE3-T142 | Tooling/change parts for SU/EB | VE3-T143 | Tool drawing /Change part finalization & approval
| Pilot BE studies | Pilot BE | VE3-T142 | Tooling/change parts for SU/EB | VE3-T144 | Tooling/change parts PR
| Pilot BE studies | Pilot BE | VE3-T142 | Tooling/change parts for SU/EB | VE3-T145 | Tooling/change parts PO to receipt
| Scale up & AMV | Scale up & AMV | - |  | VE3-T146 | Vendor qualification preparation
| Scale up & AMV | Scale up & AMV | VE3-T146 | Vendor qualification preparation | VE3-T147 | API/RM/PM vendor qualification audit clearance (if required)
| Scale up & AMV | Scale up & AMV | VE3-T146 | Vendor qualification preparation | VE3-T148 | API Vendor qualification (Docs & VQ Samples)
| Scale up & AMV | Scale up & AMV | VE3-T146 | Vendor qualification preparation | VE3-T149 | RM Vendor qualification (Docs & VQ Samples)
| Scale up & AMV | Scale up & AMV | VE3-T146 | Vendor qualification preparation | VE3-T150 | PM Vendor qualification (Docs & VQ Samples)
| Scale up & AMV | Scale up & AMV | - |  | VE3-T151 | RM Analytical method verifications
| Scale up & AMV | Scale up & AMV | VE3-T151 | RM Analytical method verifications | VE3-T152 | New Raw materials - Analytical method verifications/transfer
| Scale up & AMV | Scale up & AMV | VE3-T151 | RM Analytical method verifications | VE3-T153 | API analytical method verifications/transfer
| Scale up & AMV | Scale up & AMV | - |  | VE3-T154 | VQ Analysis
| Scale up & AMV | Scale up & AMV | VE3-T154 | VQ Analysis | VE3-T155 | API Vendor qualification analysis at QC
| Scale up & AMV | Scale up & AMV | VE3-T154 | VQ Analysis | VE3-T156 | RM Vendor qualification analysis at QC
| Scale up & AMV | Scale up & AMV | VE3-T154 | VQ Analysis | VE3-T157 | PM Vendor qualification analysis at QC
| Scale up & AMV | Scale up & AMV | VE3-T154 | VQ Analysis | VE3-T158 | API/RM & PM Spec/STPs at QA
| Scale up & AMV | Scale up & AMV | - |  | VE3-T159 | Material procurement for EB
| Scale up & AMV | Scale up & AMV | VE3-T159 | Material procurement for EB | VE3-T160 | RM BOM Finalization
| Scale up & AMV | Scale up & AMV | VE3-T159 | Material procurement for EB | VE3-T161 | API PR
| Scale up & AMV | Scale up & AMV | VE3-T159 | Material procurement for EB | VE3-T162 | API PO to receipt for EB
| Scale up & AMV | Scale up & AMV | VE3-T159 | Material procurement for EB | VE3-T163 | RM PR
| Scale up & AMV | Scale up & AMV | VE3-T159 | Material procurement for EB | VE3-T164 | RM - PO to receipt
| Scale up & AMV | Scale up & AMV | VE3-T159 | Material procurement for EB | VE3-T165 | PM BOM Finalization
| Scale up & AMV | Scale up & AMV | VE3-T159 | Material procurement for EB | VE3-T166 | PM PR
| Scale up & AMV | Scale up & AMV | VE3-T159 | Material procurement for EB | VE3-T167 | PM - PO to receipt
| Scale up & AMV | Scale up & AMV | - |  | VE3-T168 | Scale up execution
| Scale up & AMV | Scale up & AMV | VE3-T168 | Scale up execution | VE3-T169 | Scale up batches execution
| Scale up & AMV | Scale up & AMV | VE3-T168 | Scale up execution | VE3-T170 | Scale up batch analysis
| Scale up & AMV | Scale up & AMV | VE3-T168 | Scale up execution | VE3-T171 | Scale up batch report
| Scale up & AMV | Scale up & AMV | - |  | VE3-T172 | Product Analytical method validation/Transfer
| Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T173 | AMV - Feasibility (if required)
| Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T174 | AMV in-process
| Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T175 | AMV finished product
| Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T176 | AMV Forced degradation studies
| Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T177 | IP / FP Analytical Method Transfer (if required)
| Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T178 | ARD IP Spec/STPs to QA
| Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T179 | QA IP Spec/STPs to QC
| Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T180 | ARD FP Spec/STPs to QA
| Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T181 | QA FP Spec/STPs to QC
| Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T182 | Elemental impurities AMV
| Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T183 | Nitroso impurities AMV
| Scale up & AMV | Scale up & AMV | - |  | VE3-T184 | Material readiness for EB
| Scale up & AMV | Scale up & AMV | VE3-T184 | Material readiness for EB | VE3-T185 | API - Analysis & release for EB
| Scale up & AMV | Scale up & AMV | VE3-T184 | Material readiness for EB | VE3-T186 | RM - Analysis & release for EB
| Scale up & AMV | Scale up & AMV | VE3-T184 | Material readiness for EB | VE3-T187 | PM - Analysis & release for EB
| Scale up & AMV | Scale up & AMV | - |  | VE3-T188 | L2 Clearances
| Scale up & AMV | Scale up & AMV | VE3-T188 | L2 Clearances | VE3-T189 | IIG Clearance (L2)
| Scale up & AMV | Scale up & AMV | VE3-T188 | L2 Clearances | VE3-T190 | IPR Clearance (L2)
| Scale up & AMV | Scale up & AMV | VE3-T188 | L2 Clearances | VE3-T191 | Trade dress / Trademark Clearance (L2)
| Scale up & AMV | Scale up & AMV | VE3-T188 | L2 Clearances | VE3-T192 | Size & shape Clearance (L2)
| Scale up & AMV | Scale up & AMV | VE3-T188 | L2 Clearances | VE3-T193 | Costing clearance - Cost/pill (L2)
| Scale up & AMV | Scale up & AMV | - |  | VE3-T194 | Updated Risk assessment
| Scale up & AMV | Scale up & AMV | VE3-T194 | Updated Risk assessment | VE3-T195 | Updated Residual solvent assessment report (in-case of changes)
| Scale up & AMV | Scale up & AMV | VE3-T194 | Updated Risk assessment | VE3-T196 | Updated Elemental impurity risk assessment report (in-case of changes)
| Scale up & AMV | Scale up & AMV | VE3-T194 | Updated Risk assessment | VE3-T197 | Updated Genotoxic impurity risk assessment report (in-case of changes)
| Scale up & AMV | Scale up & AMV | VE3-T194 | Updated Risk assessment | VE3-T198 | Updated Nitrosamine Risk assessment report (in-case of changes)
| Scale up & AMV | Scale up & AMV | VE3-T194 | Updated Risk assessment | VE3-T199 | Updated Iron Content (in-case of changes)
| Scale up & AMV | Scale up & AMV | - |  | VE3-T200 | Exhibit batch strategy
| Scale up & AMV | Scale up & AMV | VE3-T200 | Exhibit batch strategy | VE3-T201 | Mfg. process & controls/equipment qualification range evaluation report.
| Scale up & AMV | Scale up & AMV | - |  | VE3-T202 | Phase gate 4 clearances
| Scale up & AMV | Scale up & AMV | VE3-T202 | Phase gate 4 clearances | VE3-T203 | Master Formula Card (MFC)
| Scale up & AMV | Scale up & AMV | VE3-T202 | Phase gate 4 clearances | VE3-T204 | Master Packaging Card (MPC)
| Exhibit batches | Exhibit batches | - |  | VE3-T205 | EB Documentation
| Exhibit batches | Exhibit batches | VE3-T205 | EB Documentation | VE3-T206 | Change control (initiation to approval)
| Exhibit batches | Exhibit batches | VE3-T205 | EB Documentation | VE3-T207 | Cleaning validation protocol
| Exhibit batches | Exhibit batches | VE3-T205 | EB Documentation | VE3-T208 | Batch production records
| Exhibit batches | Exhibit batches | VE3-T205 | EB Documentation | VE3-T209 | Batch manufacturing records
| Exhibit batches | Exhibit batches | VE3-T205 | EB Documentation | VE3-T210 | Batch packing records
| Exhibit batches | Exhibit batches | VE3-T205 | EB Documentation | VE3-T211 | Exhibit batch protocols (Sampling/Hold time)
| Exhibit batches | Exhibit batches | VE3-T205 | EB Documentation | VE3-T212 | Stability protocols
| Exhibit batches | Exhibit batches | - |  | VE3-T213 | EB Manufacturing
| Exhibit batches | Exhibit batches | VE3-T213 | EB Manufacturing | VE3-T214 | Exhibit batch manufacturing - Blend stage
| Exhibit batches | Exhibit batches | VE3-T213 | EB Manufacturing | VE3-T215 | Exhibit batch IP Stage testing & release
| Exhibit batches | Exhibit batches | VE3-T213 | EB Manufacturing | VE3-T216 | Exhibit batch manufacturing - FP Stage
| Exhibit batches | Exhibit batches | VE3-T213 | EB Manufacturing | VE3-T217 | Exhibit batch FP Stage testing & release
| Exhibit batches | Exhibit batches | VE3-T213 | EB Manufacturing | VE3-T218 | Exhibit batch packaging
| Exhibit batches | Exhibit batches | VE3-T213 | EB Manufacturing | VE3-T219 | Stability date in
| Exhibit batches | Exhibit batches | - |  | VE3-T220 | EB Sample analysis
| Exhibit batches | Exhibit batches | VE3-T220 | EB Sample analysis | VE3-T221 | EB Protocol bound sample data generation
| Exhibit batches | Exhibit batches | - |  | VE3-T222 | Other studies on EB Samples
| Exhibit batches | Exhibit batches | VE3-T222 | Other studies on EB Samples | VE3-T223 | In-use stability studies
| Exhibit batches | Exhibit batches | VE3-T222 | Other studies on EB Samples | VE3-T224 | Photostability studies
| Exhibit batches | Exhibit batches | VE3-T222 | Other studies on EB Samples | VE3-T225 | Split studies
| Exhibit batches | Exhibit batches | VE3-T222 | Other studies on EB Samples | VE3-T226 | Alcohol dose dumping studies (if applicable)
| Exhibit batches | Exhibit batches | VE3-T222 | Other studies on EB Samples | VE3-T227 | Transportation studies
| Exhibit batches | Exhibit batches | VE3-T222 | Other studies on EB Samples | VE3-T228 | XRD data generation
| Exhibit batches | Exhibit batches | - |  | VE3-T229 | Pivotal BE Preparation
| Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T230 | Pivotal BE Study Protocols readiness
| Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T231 | BENOC documents submission
| Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T232 | Test license/BENOC for pivotal BE
| Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T233 | RLD for Pivotal BE studies
| Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T234 | RLD COA generation
| Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T235 | Test (EB) & RLD 12 units release medium dissolution
| Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T236 | Test (EB) & RLD 12 units multi media dissolutions
| Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T237 | Note for approval for Pivotal BE (Technical)
| Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T238 | Note for approval for Pivotal BE (Budget & PR, PO)
| Pivotal BE studies | Pivotal BE | - |  | VE3-T239 | Phase gate 5 clearance
| Pivotal BE studies | Pivotal BE | - |  | VE3-T240 | Pivotal BE Studies
| Pivotal BE studies | Pivotal BE | VE3-T240 | Pivotal BE Studies | VE3-T241 | BE samples shipment to CRO
| Pivotal BE studies | Pivotal BE | VE3-T240 | Pivotal BE Studies | VE3-T242 | Fasting pivotal study (Clinic start - End)
| Pivotal BE studies | Pivotal BE | VE3-T240 | Pivotal BE Studies | VE3-T243 | Fasting study results
| Pivotal BE studies | Pivotal BE | VE3-T240 | Pivotal BE Studies | VE3-T244 | Fed pivotal study (Clinic start - End)
| Pivotal BE studies | Pivotal BE | VE3-T240 | Pivotal BE Studies | VE3-T245 | Fed Study results
| Pivotal BE studies | Pivotal BE | VE3-T240 | Pivotal BE Studies | VE3-T246 | Other studies if any
| Pivotal BE studies | Pivotal BE | - |  | VE3-T247 | Any other studies (Suspension/NG tube /Apple sauce etc..)
| Dossier filing | Filing | - |  | VE3-T248 | L3 Clearances
| Dossier filing | Filing | VE3-T248 | L3 Clearances | VE3-T249 | Costing clearance (L3)
| Dossier filing | Filing | - |  | VE3-T250 | Intended Documents readiness
| Dossier filing | Filing | VE3-T250 | Intended Documents readiness | VE3-T251 | EB reports availability
| Dossier filing | Filing | VE3-T250 | Intended Documents readiness | VE3-T252 | Master Formula Record readiness
| Dossier filing | Filing | VE3-T250 | Intended Documents readiness | VE3-T253 | Intended Docs preparation
| Dossier filing | Filing | - |  | VE3-T254 | PDR readiness
| Dossier filing | Filing | - |  | VE3-T255 | Pivotal BE studies report availability
| Dossier filing | Filing | - |  | VE3-T256 | 3M stability data availability
| Dossier filing | Filing | - |  | VE3-T257 | 6M stability data availability
| Dossier filing | Filing | - |  | VE3-T258 | Phase gate 6 clearance (Costing, docs as per RA checklist )
| Dossier filing | Filing | - |  | VE3-T259 | Filing