## Metoprolol
S.No | Milestone Name | Task List Name | Parent Task ID | Parent Task Name | Task ID | Task Name | Owner | Department | Dependency status | Critical Task | Predecessors | Successors | Status | Due Date
1 | Project initiation | Project initiation | - |  | VE3-T1 | Project introduction form (PIF) | V Naidu Kalamata | PM | Independent tasks | false |  |  | Completed
2 | Project initiation | Project initiation | - |  | VE3-T2 | Agreement (in case of Co-Development ) | V Naidu Kalamata | PM | Blocking tasks | true |  | VE3-T3 | Completed |  | This is only for new products
3 | Project initiation | Project initiation | - |  | VE3-T3 | Project kickoff | V Naidu Kalamata | PM | Waiting for tasks | true | VE3-T2 | VE3-T9 | Completed
4 | Full kit for Product Development | Fullkitting | - |  | VE3-T4 | Product Development Strategy Note (PDSN) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
5 | Full kit for Product Development | Fullkitting | VE3-T4 | Product Development Strategy Note (PDSN) | VE3-T5 | IP CLSF Report | Vani Bhattu | PM | Independent tasks | false |  |  | Completed
6 | Full kit for Product Development | Fullkitting | VE3-T4 | Product Development Strategy Note (PDSN) | VE3-T6 | Regulatory strategy note | RA | RA | Independent tasks | false |  |  | Completed
7 | Full kit for Product Development | Fullkitting | VE3-T4 | Product Development Strategy Note (PDSN) | VE3-T7 | Marketing Requirements (Pack mode & special interest based on market demand) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
8 | Full kit for Product Development | Fullkitting | VE3-T4 | Product Development Strategy Note (PDSN) | VE3-T8 | PDSN Preparation | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
9 | Full kit for Product Development | Fullkitting | - |  | VE3-T9 | Licenses - R&D Centre | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T3 | VE3-T44 | Completed
10 | Full kit for Product Development | Fullkitting | VE3-T9 | Licenses - R&D Centre | VE3-T10 | NOC for API (if applicable) - R&D Centre | sadasivudu.pothana | F R&D | Blocking tasks | true |  | VE3-T11 | Completed
11 | Full kit for Product Development | Fullkitting | VE3-T9 | Licenses - R&D Centre | VE3-T11 | NOC for Finished product (if applicable) - R&D Centre | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T10 | VE3-T12 | Completed
12 | Full kit for Product Development | Fullkitting | VE3-T9 | Licenses - R&D Centre | VE3-T12 | Test license availability - R&D Centre | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T11 |  | Completed
13 | Full kit for Product Development | Fullkitting | VE3-T9 | Licenses - R&D Centre | VE3-T13 | API Import license (if required) - R&D Centre | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
14 | Full kit for Product Development | Fullkitting | - |  | VE3-T14 | Licenses - GMP Facility | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T120 | Completed
15 | Full kit for Product Development | Fullkitting | VE3-T14 | Licenses - GMP Facility | VE3-T15 | NOC for API (if applicable) - GMP Facility | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T16 | Completed
16 | Full kit for Product Development | Fullkitting | VE3-T14 | Licenses - GMP Facility | VE3-T16 | NOC for Finished product (if applicable) - GMP Facility | sadasivudu.pothana | F R&D | Waiting for tasks | false | VE3-T15 | VE3-T17 | Completed
17 | Full kit for Product Development | Fullkitting | VE3-T14 | Licenses - GMP Facility | VE3-T17 | Test license availability - GMP Facility | sadasivudu.pothana | F R&D | Waiting for tasks | false | VE3-T16 | VE3-T121 | Completed
18 | Full kit for Product Development | Fullkitting | VE3-T14 | Licenses - GMP Facility | VE3-T18 | API import license (if required) - GMP Facility | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T121 | Completed
19 | Full kit for Product Development | Fullkitting | - |  | VE3-T19 | Licenses - RLD | sadasivudu.pothana | F R&D | Blocking tasks | true |  | VE3-T32 | Completed
20 | Full kit for Product Development | Fullkitting | VE3-T19 | Licenses - RLD | VE3-T20 | RLD - NOC (if Applicable) | sadasivudu.pothana | F R&D | Blocking tasks | true |  | VE3-T21 | Completed
21 | Full kit for Product Development | Fullkitting | VE3-T19 | Licenses - RLD | VE3-T21 | RLD Import license | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T20 | VE3-T35 | Completed
22 | Full kit for Product Development | Fullkitting | - |  | VE3-T22 | IH API for Development | sampath.upparapalli | API | Blocking tasks | false |  | VE3-T44 | Completed |  | Required for other products
23 | Full kit for Product Development | Fullkitting | VE3-T22 | IH API for Development | VE3-T23 | IH API Requirement - Note For approval | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T24 | Completed
24 | Full kit for Product Development | Fullkitting | VE3-T22 | IH API for Development | VE3-T24 | IH API receipt for development | sampath.upparapalli | API | Waiting for tasks | false | VE3-T23 |  | Completed
25 | Full kit for Product Development | Fullkitting | VE3-T22 | IH API for Development | VE3-T25 | IH API related docs (Characterization data/ Impurities declaration etc) | sampath.upparapalli | API | Independent tasks | false |  |  | Completed
26 | Full kit for Product Development | Fullkitting | VE3-T22 | IH API for Development | VE3-T26 | IH API Techpack / O DMF availability | sampath.upparapalli | API | Independent tasks | false |  |  | Completed
27 | Full kit for Product Development | Fullkitting | - |  | VE3-T27 | OS API for Development | naresh.nalajala | SCM | Blocking tasks | false |  | VE3-T44 | Completed
28 | Full kit for Product Development | Fullkitting | VE3-T27 | OS API for Development | VE3-T28 | OS API Requirement - Note For approval | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
29 | Full kit for Product Development | Fullkitting | VE3-T27 | OS API for Development | VE3-T29 | OS API receipt for development | naresh.nalajala | SCM | Independent tasks | false |  |  | Completed
30 | Full kit for Product Development | Fullkitting | VE3-T27 | OS API for Development | VE3-T30 | OS API related docs (Characterization data/ Impurities declaration etc) | naresh.nalajala | SCM | Independent tasks | false |  |  | Completed
31 | Full kit for Product Development | Fullkitting | VE3-T27 | OS API for Development | VE3-T31 | OS API Techpack / O DMF availability | naresh.nalajala | SCM | Independent tasks | false |  |  | Completed
32 | Full kit for Product Development | Fullkitting | - |  | VE3-T32 | RLD availability for Development | PM | PM | Waiting for tasks | true | VE3-T19 | VE3-T44 | Completed
33 | Full kit for Product Development | Fullkitting | VE3-T32 | RLD availability for Development | VE3-T33 | RLD Requirement - Note For approval | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T34 | Completed
34 | Full kit for Product Development | Fullkitting | VE3-T32 | RLD availability for Development | VE3-T34 | RLD PR / PO | PM | PM | Waiting for tasks | false | VE3-T33 | VE3-T35 | Completed
35 | Full kit for Product Development | Fullkitting | VE3-T32 | RLD availability for Development | VE3-T35 | RLD Receipt | PM | PM | Waiting for tasks | true | VE3-T34,VE3-T21 | VE3-T45 | Completed
36 | Full kit for Product Development | Fullkitting | - |  | VE3-T36 | Excipients availability for Development | naresh.nalajala | SCM | Blocking tasks | false |  | VE3-T44 | Completed
37 | Full kit for Product Development | Fullkitting | VE3-T36 | Excipients availability for Development | VE3-T37 | New excipients request (if any) to SCM | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T39,VE3-T38 | Completed
38 | Full kit for Product Development | Fullkitting | VE3-T36 | Excipients availability for Development | VE3-T38 | Sample quantity arrangement (along with Docs) | naresh.nalajala | SCM | Waiting for tasks | false | VE3-T37 |  | Completed
39 | Full kit for Product Development | Fullkitting | VE3-T36 | Excipients availability for Development | VE3-T39 | New excipients PR (If req) | Vani Bhattu | PM | Waiting for tasks | false | VE3-T37 | VE3-T40 | Completed
40 | Full kit for Product Development | Fullkitting | VE3-T36 | Excipients availability for Development | VE3-T40 | New excipients PO to receipt | naresh.nalajala | SCM | Waiting for tasks | false | VE3-T39 |  | Completed
41 | Full kit for Product Development | Fullkitting | - |  | VE3-T41 | Packing material availability for Development | PM | PM | Blocking tasks | true |  | VE3-T44 | Completed
42 | Full kit for Product Development | Fullkitting | - |  | VE3-T42 | Analytical requirements readiness | narendra.thamma kumar | F AR&D | Blocking tasks | false |  | VE3-T90 | Completed
43 | Full kit for Product Development | Fullkitting | - |  | VE3-T43 | Phase gate 1 clearance | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T81 | Completed
44 | Development | Formulation Development | - |  | VE3-T44 | Prototype development | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T22,VE3-T27,VE3-T36,VE3-T9,VE3-T32,VE3-T41 | VE3-T56 | Completed
45 | Development | Formulation Development | VE3-T44 | Prototype development | VE3-T45 | RLD characterization | sadasivudu.pothana | F R&D | Waiting for tasks | false | VE3-T35 | VE3-T46,VE3-T47 | Completed
46 | Development | Formulation Development | VE3-T44 | Prototype development | VE3-T46 | Tooling/change parts for development | sadasivudu.pothana | F R&D | Waiting for tasks | false | VE3-T45 |  | Completed |  |  | If Required
47 | Development | Formulation Development | VE3-T44 | Prototype development | VE3-T47 | Packing configuration finalization | sadasivudu.pothana | F R&D | Waiting for tasks | false | VE3-T45 |  | Completed
48 | Development | Formulation Development | VE3-T44 | Prototype development | VE3-T48 | Preformulation studies (Drug Excipient compatibility studies, PXRD etc.) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
49 | Development | Formulation Development | VE3-T44 | Prototype development | VE3-T49 | Risk assessment of formulation (QTPP, CQA & CMAs but not limited to) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
50 | Development | Formulation Development | VE3-T44 | Prototype development | VE3-T50 | Risk assessment of process (CPP but not limited to) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
51 | Development | Formulation Development | VE3-T44 | Prototype development | VE3-T51 | Risk assessment of packing (CMA but not limited to) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
52 | Development | Formulation Development | VE3-T44 | Prototype development | VE3-T52 | Dissolution mapping in release medium | sadasivudu.pothana | F R&D | Blocking tasks | true |  | VE3-T53 SS | Completed
53 | Development | Formulation Development | VE3-T44 | Prototype development | VE3-T53 | Dissolution mapping in multimedia | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T52 SS,VE3-T54 SS |  | Completed
54 | Development | Formulation Development | VE3-T44 | Prototype development | VE3-T54 | Dissolution mapping in biorelevant dissolution conditions (if required) | sadasivudu.pothana | F R&D | Blocking tasks | true |  | VE3-T53 SS | Completed
55 | Development | Formulation Development | VE3-T44 | Prototype development | VE3-T55 | Stress stability (accelerated conditions like heat, humidity, open exposure etc.) | sadasivudu.pothana | F R&D | Independent tasks | true |  |  | Completed
56 | Development | Formulation Development | - |  | VE3-T56 | Formulation finalization | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T44 | VE3-T120 | Completed
57 | Development | Formulation Development | VE3-T56 | Formulation finalization | VE3-T57 | Formulation optimization | sadasivudu.pothana | F R&D | Independent tasks | true |  |  | Completed
58 | Development | Formulation Development | VE3-T56 | Formulation finalization | VE3-T58 | Process optimization | sadasivudu.pothana | F R&D | Independent tasks | true |  |  | Completed
59 | Development | Formulation Development | VE3-T56 | Formulation finalization | VE3-T59 | Discriminatory dissolution trials | sadasivudu.pothana | F R&D | Independent tasks | true |  |  | Completed
60 | Development | Formulation Development | - |  | VE3-T60 | API availability for Pilot BE batches | naresh.nalajala | SCM | Blocking tasks | false |  | VE3-T120 | Completed
61 | Development | Formulation Development | VE3-T60 | API availability for Pilot BE batches | VE3-T61 | IH API for pilot BE Batches | sampath.upparapalli | API | Blocking tasks | false |  | VE3-T121 | Completed
62 | Development | Formulation Development | VE3-T60 | API availability for Pilot BE batches | VE3-T62 | IH API Declarations (EI, RSL, GTI, Benzene content, Stab data etc) | sampath.upparapalli | API | Blocking tasks | false |  | VE3-T121 | Completed
[6 empty] | Excepients Declaration(EI, RSL, GTI, Benzene content, Stab data etc) | [6 empty] | Completed
63 | Development | Formulation Development | VE3-T60 | API availability for Pilot BE batches | VE3-T63 | OS API PR for pilot BE Batches | naresh.nalajala | SCM | Blocking tasks | false |  | VE3-T64 | Completed
64 | Development | Formulation Development | VE3-T60 | API availability for Pilot BE batches | VE3-T64 | OS API PO to receipt for pilot BE Batches | naresh.nalajala | SCM | Waiting for tasks | false | VE3-T63 | VE3-T121 | Completed
65 | Development | Formulation Development | - |  | VE3-T65 | Excipient for Pilot BE batches | naresh.nalajala | SCM | Blocking tasks | false |  | VE3-T120 | Completed
66 | Development | Formulation Development | VE3-T65 | Excipient for Pilot BE batches | VE3-T66 | BOM Finalization | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T67 | Completed
67 | Development | Formulation Development | VE3-T65 | Excipient for Pilot BE batches | VE3-T67 | PR Release | Vani Bhattu | PM | Waiting for tasks | false | VE3-T66 | VE3-T68 | Completed
68 | Development | Formulation Development | VE3-T65 | Excipient for Pilot BE batches | VE3-T68 | PO Release & RM receipt | naresh.nalajala | SCM | Waiting for tasks | false | VE3-T67 | VE3-T121 | Completed
69 | Development | Formulation Development | - |  | VE3-T69 | Pilot BE - Preparation | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T128 | Completed
70 | Development | Formulation Development | VE3-T69 | Pilot BE - Preparation | VE3-T70 | BE CRO Selection & Qualification (if required) | Ayyappa Kapuganti | BE Study Coordinator | Blocking tasks | false |  | VE3-T72 | Completed
71 | Development | Formulation Development | VE3-T69 | Pilot BE - Preparation | VE3-T71 | RLD availability for Pilot BE study | PM | PM | Independent tasks | false |  |  | Completed
72 | Development | Formulation Development | VE3-T69 | Pilot BE - Preparation | VE3-T72 | Pilot BE Study Protocols readiness | Ayyappa Kapuganti | BE Study Coordinator | Waiting for tasks | false | VE3-T70 | VE3-T74 | Completed
73 | Development | Formulation Development | VE3-T69 | Pilot BE - Preparation | VE3-T73 | BENOC Document submission | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T74 | Completed
74 | Development | Formulation Development | VE3-T69 | Pilot BE - Preparation | VE3-T74 | Test license/BENOC for Pilot BE | Ayyappa Kapuganti | BE Study Coordinator | Waiting for tasks | false | VE3-T72,VE3-T73 |  | Completed
75 | Development | Formulation Development | - |  | VE3-T75 | Risk assessment | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
76 | Development | Formulation Development | VE3-T75 | Risk assessment | VE3-T76 | Residual solvents risk assessment report | narendra.thamma kumar | F AR&D | Independent tasks | false |  |  | Completed
77 | Development | Formulation Development | VE3-T75 | Risk assessment | VE3-T77 | Genotoxic impurities risk assessment report | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
78 | Development | Formulation Development | VE3-T75 | Risk assessment | VE3-T78 | Elemental impurities risk assessment report | narendra.thamma kumar | F AR&D | Independent tasks | false |  |  | Completed
79 | Development | Formulation Development | VE3-T75 | Risk assessment | VE3-T79 | Nitrosamine risk assessment report | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
80 | Development | Formulation Development | VE3-T75 | Risk assessment | VE3-T80 | Iron content assessment report | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
81 | Development | Formulation Development | - |  | VE3-T81 | Phase gate 2 clearance | sadasivudu.pothana | F R&D | Waiting for tasks | false | VE3-T43 | VE3-T127 | Completed
82 | Development | Formulation Development | - |  | VE3-T82 | 1M stability of prototype formulation | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
83 | Development | Formulation Development | - |  | VE3-T83 | 2M stability of prototype formulation | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
84 | Development | Formulation Development | - |  | VE3-T84 | 3M stability of prototype formulation | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
85 | Development | Analytical development | - |  | VE3-T85 | Residue method development | narendra.thamma kumar | F AR&D | Blocking tasks | false |  | VE3-T205 | Completed
86 | Development | Analytical development | VE3-T85 | Residue method development | VE3-T86 | Residue method IOC & Sample submission | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T87 | Completed
87 | Development | Analytical development | VE3-T85 | Residue method development | VE3-T87 | Residue/cleaning method development | narendra.thamma kumar | F AR&D | Waiting for tasks | false | VE3-T86 | VE3-T88 | Completed
88 | Development | Analytical development | VE3-T85 | Residue method development | VE3-T88 | Residue/cleaning method fullkit to QC | narendra.thamma kumar | F AR&D | Waiting for tasks | false | VE3-T87 | VE3-T89 | Completed
89 | Development | Analytical development | VE3-T85 | Residue method development | VE3-T89 | AMV of Residue/cleaning method at QC | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | false | VE3-T88 |  | Completed
90 | Development | Analytical development | - |  | VE3-T90 | Analytical method development by QbD | narendra.thamma kumar | F AR&D | Waiting for tasks | false | VE3-T42 | VE3-T172 | Completed
91 | Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T91 | AMD Sample submission with Spec IOC | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T92,VE3-T93 | Completed
92 | Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T92 | Analytical method development in-process | narendra.thamma kumar | F AR&D | Waiting for tasks | false | VE3-T91 | VE3-T99 | Completed
93 | Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T93 | Analytical method development finished product | narendra.thamma kumar | F AR&D | Waiting for tasks | false | VE3-T91 | VE3-T99 | Completed
94 | Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T94 | Forced degradation studies | narendra.thamma kumar | F AR&D | Independent tasks | false |  |  | Completed
95 | Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T95 | Solubility profile data generation | narendra.thamma kumar | F AR&D | Independent tasks | false |  |  | Completed
96 | Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T96 | Dissolution method development-Release medium | narendra.thamma kumar | F AR&D | Independent tasks | false |  |  | Completed
97 | Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T97 | Dissolution method development-Multi media | narendra.thamma kumar | F AR&D | Independent tasks | false |  |  | Completed
98 | Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T98 | Dissolution method development-Bio-relevant (if required) | narendra.thamma kumar | F AR&D | Independent tasks | false |  |  | Completed
99 | Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T99 | IP & FP specification finalization & justification | sadasivudu.pothana | F R&D | Waiting for tasks | false | VE3-T92,VE3-T93 | VE3-T101 | Completed
100 | Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T100 | AMV Sample submission | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T101 | Completed
101 | Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T101 | AMV Sample COA generation & Fullkit to QC | narendra.thamma kumar | F AR&D | Waiting for tasks | false | VE3-T99,VE3-T100 | VE3-T174,VE3-T175 | Completed
102 | Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T102 | Elemental impurities AMD - IOC & Sample submission | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T103 | Completed
103 | Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T103 | Elemental impurities AMD & full kit to QC (if required) | narendra.thamma kumar | F AR&D | Waiting for tasks | false | VE3-T102 | VE3-T182 | Completed
104 | Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T104 | Nitroso impurities AMD - IOC & Sample submission | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T105 | Completed
105 | Development | Analytical development | VE3-T90 | Analytical method development by QbD | VE3-T105 | Nitroso impurities AMD & full kit to QC (if required) | narendra.thamma kumar | F AR&D | Waiting for tasks | false | VE3-T104 | VE3-T183 | Completed
106 | Development | Analytical development | - |  | VE3-T106 | New Raw materials - Analytical method | narendra.thamma kumar | F AR&D | Blocking tasks | true |  | VE3-T151 | Completed
107 | Development | Analytical development | VE3-T106 | New Raw materials - Analytical method | VE3-T107 | API submission for Method feasibility with IOC | sadasivudu.pothana | F R&D | Blocking tasks | true |  | VE3-T108 | Completed
108 | Development | Analytical development | VE3-T106 | New Raw materials - Analytical method | VE3-T108 | API Analytical method feasibility testing & ful kit to QC (in-case of outsourced APIs) | narendra.thamma kumar | F AR&D | Waiting for tasks | true | VE3-T107 | VE3-T109 | Completed
109 | Development | Analytical development | VE3-T106 | New Raw materials - Analytical method | VE3-T109 | API specification finalization & justification (in-case of outsourced APIs) | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T108 | VE3-T153 | Completed
110 | Development | Analytical development | VE3-T106 | New Raw materials - Analytical method | VE3-T110 | New Raw materials - IOC & Sample submission to FARD | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T111 | Completed |  | No required for this product(KCL Required)
111 | Development | Analytical development | VE3-T106 | New Raw materials - Analytical method | VE3-T111 | New Raw materials - Feasibility testing | narendra.thamma kumar | F AR&D | Waiting for tasks | false | VE3-T110 | VE3-T112 | Completed |  | No required for this product
112 | Development | Analytical development | VE3-T106 | New Raw materials - Analytical method | VE3-T112 | New Raw materials - Full kit to QC | narendra.thamma kumar | F AR&D | Waiting for tasks | false | VE3-T111 | VE3-T152 | Completed |  | No required for this product
113 | Development | Analytical development | VE3-T106 | New Raw materials - Analytical method | VE3-T113 | Method equivalency testing (if any) | narendra.thamma kumar | F AR&D | Independent tasks | true |  |  | Completed
114 | Pilot BE studies | Pilot BE | - |  | VE3-T114 | L1 Clearances | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
115 | Pilot BE studies | Pilot BE | VE3-T114 | L1 Clearances | VE3-T115 | IIG Clearance (L1) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
116 | Pilot BE studies | Pilot BE | VE3-T114 | L1 Clearances | VE3-T116 | IPR Clearance (L1) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
117 | Pilot BE studies | Pilot BE | VE3-T114 | L1 Clearances | VE3-T117 | Trade dress / Trademark Clearance (L1) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
118 | Pilot BE studies | Pilot BE | VE3-T114 | L1 Clearances | VE3-T118 | Size & shape Clearance (L1) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
119 | Pilot BE studies | Pilot BE | VE3-T114 | L1 Clearances | VE3-T119 | Product Costing clearance - Cost/pill (L1) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  | Completed
120 | Pilot BE studies | Pilot BE | - |  | VE3-T120 | Pilot BE IPs readiness | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T14,VE3-T65,VE3-T60,VE3-T56 | VE3-T128 | Completed
121 | Pilot BE studies | Pilot BE | VE3-T120 | Pilot BE IPs readiness | VE3-T121 | Pilot BE batch(es) manufacturing | sadasivudu.pothana | F R&D | Waiting for tasks | false | VE3-T18,VE3-T17,VE3-T64,VE3-T68,VE3-T61,VE3-T62 | VE3-T122,VE3-T123 | Completed
122 | Pilot BE studies | Pilot BE | VE3-T120 | Pilot BE IPs readiness | VE3-T122 | Pilot BE Test batch(es) analysis (CoA, release and multimedia dissolutions) | narendra.thamma kumar | F AR&D | Waiting for tasks | false | VE3-T121 | VE3-T124 | Completed
123 | Pilot BE studies | Pilot BE | VE3-T120 | Pilot BE IPs readiness | VE3-T123 | Pilot BE RLD analysis (CoA, release and multimedia dissolutions) | narendra.thamma kumar | F AR&D | Waiting for tasks | false | VE3-T121 | VE3-T124 | Completed
124 | Pilot BE studies | Pilot BE | VE3-T120 | Pilot BE IPs readiness | VE3-T124 | Note for Approval for Pilot BE study (Technical) | sadasivudu.pothana | F R&D | Waiting for tasks | false | VE3-T122,VE3-T123 | VE3-T125 | Completed
125 | Pilot BE studies | Pilot BE | VE3-T120 | Pilot BE IPs readiness | VE3-T125 | Note for Approval for Pilot BE study - Budget/PR / PO Release | PM | PM | Waiting for tasks | false | VE3-T124 |  | Completed
126 | Pilot BE studies | Pilot BE | VE3-T120 | Pilot BE IPs readiness | VE3-T126 | IPs shipment to CRO | Ayyappa Kapuganti | BE Study Coordinator | Blocking tasks | true |  | VE3-T129,VE3-T131 | Completed
127 | Pilot BE studies | Pilot BE | - |  | VE3-T127 | Phase gate 3 clearance | sadasivudu.pothana | F R&D | Waiting for tasks | false | VE3-T81 |  | Completed
128 | Pilot BE studies | Pilot BE | - |  | VE3-T128 | Pilot BE Study(ies) | Ayyappa Kapuganti | BE Study Coordinator | Waiting for tasks | true | VE3-T69,VE3-T120 | VE3-T205,VE3-T229 | Completed
129 | Pilot BE studies | Pilot BE | VE3-T128 | Pilot BE Study(ies) | VE3-T129 | Fasting pilot BE study (Clinic Start - End) | Ayyappa Kapuganti | BE Study Coordinator | Waiting for tasks | true | VE3-T126 | VE3-T130 | Completed
130 | Pilot BE studies | Pilot BE | VE3-T128 | Pilot BE Study(ies) | VE3-T130 | Fasting study results | Ayyappa Kapuganti | BE Study Coordinator | Waiting for tasks | true | VE3-T129 |  | Completed
131 | Pilot BE studies | Pilot BE | VE3-T128 | Pilot BE Study(ies) | VE3-T131 | Fed pilot BE study (Clinic Start - End) | Ayyappa Kapuganti | BE Study Coordinator | Waiting for tasks | true | VE3-T126 | VE3-T132 | Completed
132 | Pilot BE studies | Pilot BE | VE3-T128 | Pilot BE Study(ies) | VE3-T132 | Fed study results | Ayyappa Kapuganti | BE Study Coordinator | Waiting for tasks | true | VE3-T131 |  | Completed
133 | Pilot BE studies | Pilot BE | VE3-T128 | Pilot BE Study(ies) | VE3-T133 | Any other studies | Ayyappa Kapuganti | BE Study Coordinator | Independent tasks | false |  |  | Completed
134 | Pilot BE studies | Pilot BE | - |  | VE3-T134 | Material procurement for scale up | naresh.nalajala | SCM | Blocking tasks | true |  | VE3-T168 | Completed
135 | Pilot BE studies | Pilot BE | VE3-T134 | Material procurement for scale up | VE3-T135 | BOM Submission for SU | sadasivudu.pothana | F R&D | Blocking tasks | true |  | VE3-T147,VE3-T148,VE3-T149,VE3-T150,VE3-T136,VE3-T140,VE3-T138 | Completed
136 | Pilot BE studies | Pilot BE | VE3-T134 | Material procurement for scale up | VE3-T136 | API PR | PM | PM | Waiting for tasks | false | VE3-T135 | VE3-T137 | Completed
137 | Pilot BE studies | Pilot BE | VE3-T134 | Material procurement for scale up | VE3-T137 | API PO to receipt | naresh.nalajala | SCM | Waiting for tasks | false | VE3-T136 |  | Completed
138 | Pilot BE studies | Pilot BE | VE3-T134 | Material procurement for scale up | VE3-T138 | RM PR | PM | PM | Waiting for tasks | false | VE3-T135 | VE3-T139 | Completed
139 | Pilot BE studies | Pilot BE | VE3-T134 | Material procurement for scale up | VE3-T139 | RM PO to receipt | naresh.nalajala | SCM | Waiting for tasks | false | VE3-T138 |  | Completed
140 | Pilot BE studies | Pilot BE | VE3-T134 | Material procurement for scale up | VE3-T140 | PM PR | PM | PM | Waiting for tasks | false | VE3-T135 | VE3-T141 | Completed
141 | Pilot BE studies | Pilot BE | VE3-T134 | Material procurement for scale up | VE3-T141 | PM PO to receipt | PM | PM | Waiting for tasks | false | VE3-T140 |  | Completed
142 | Pilot BE studies | Pilot BE | - |  | VE3-T142 | Tooling/change parts for SU/EB | PM | PM | Blocking tasks | true |  | VE3-T168 | Completed |  | No required for this prodt, required for all pro
143 | Pilot BE studies | Pilot BE | VE3-T142 | Tooling/change parts for SU/EB | VE3-T143 | Tool drawing /Change part finalization & approval | sadasivudu.pothana | F R&D | Blocking tasks | true |  | VE3-T144 | Completed |  | No required for this prodt, required for all pro
144 | Pilot BE studies | Pilot BE | VE3-T142 | Tooling/change parts for SU/EB | VE3-T144 | Tooling/change parts PR | PM | PM | Waiting for tasks | true | VE3-T143 | VE3-T145 | Completed |  | No required for this prodt, required for all pro
145 | Pilot BE studies | Pilot BE | VE3-T142 | Tooling/change parts for SU/EB | VE3-T145 | Tooling/change parts PO to receipt | PM | PM | Waiting for tasks | true | VE3-T144 |  | Completed |  | No required for this prodt, required for all pro
146 | Scale up & AMV | Scale up & AMV | - |  | VE3-T146 | Vendor qualification preparation | naresh.nalajala | SCM | Blocking tasks | true |  | VE3-T154 |  | 2026-09-16 | No required for this prodt, required for all pro
147 | Scale up & AMV | Scale up & AMV | VE3-T146 | Vendor qualification preparation | VE3-T147 | API/RM/PM vendor qualification audit clearance (if required) | satyanarayana.perabathula | AQA | Waiting for tasks | true | VE3-T135 | VE3-T148,VE3-T149,VE3-T150 |  | 2026-09-16 | No required for this prodt, required for all pro,KCL tool
148 | Scale up & AMV | Scale up & AMV | VE3-T146 | Vendor qualification preparation | VE3-T148 | API Vendor qualification (Docs & VQ Samples) | naresh.nalajala | SCM | Waiting for tasks | true | VE3-T135,VE3-T147 | VE3-T155 |  | 2026-09-16 | No required for this prodt, required for all pro
149 | Scale up & AMV | Scale up & AMV | VE3-T146 | Vendor qualification preparation | VE3-T149 | RM Vendor qualification (Docs & VQ Samples) | naresh.nalajala | SCM | Waiting for tasks | true | VE3-T135,VE3-T147 | VE3-T152 |  | 2026-09-16 | No required for this prodt, required for all pro
150 | Scale up & AMV | Scale up & AMV | VE3-T146 | Vendor qualification preparation | VE3-T150 | PM Vendor qualification (Docs & VQ Samples) | naresh.nalajala | SCM | Waiting for tasks | true | VE3-T135,VE3-T147 | VE3-T157 |  | 2026-09-16 | No required for this prodt, required for all pro
151 | Scale up & AMV | Scale up & AMV | - |  | VE3-T151 | RM Analytical method verifications | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | true | VE3-T106 |  |  | 2026-09-16 | No required for this prodt, required for all pro
152 | Scale up & AMV | Scale up & AMV | VE3-T151 | RM Analytical method verifications | VE3-T152 | New Raw materials - Analytical method verifications/transfer | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | false | VE3-T112,VE3-T149 | VE3-T156 |  | 2026-09-16 | No required for this prodt, required for all pro, KCL
153 | Scale up & AMV | Scale up & AMV | VE3-T151 | RM Analytical method verifications | VE3-T153 | API analytical method verifications/transfer | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | true | VE3-T109 | VE3-T155 |  | 2026-09-16 | No required for this prodt, required for all pro, KCL
154 | Scale up & AMV | Scale up & AMV | - |  | VE3-T154 | VQ Analysis | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | true | VE3-T146 | VE3-T184 |  | 2026-09-16 | No required for this prodt, required for all pro, KCL
155 | Scale up & AMV | Scale up & AMV | VE3-T154 | VQ Analysis | VE3-T155 | API Vendor qualification analysis at QC | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | true | VE3-T148,VE3-T153 | VE3-T158 |  | 2026-09-16 | No required for this prodt, required for all pro
156 | Scale up & AMV | Scale up & AMV | VE3-T154 | VQ Analysis | VE3-T156 | RM Vendor qualification analysis at QC | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | false | VE3-T152 | VE3-T158 |  | 2026-09-16 | No required for this prodt, required for all pro
157 | Scale up & AMV | Scale up & AMV | VE3-T154 | VQ Analysis | VE3-T157 | PM Vendor qualification analysis at QC | PM | PM | Waiting for tasks | true | VE3-T150 | VE3-T158 |  | 2026-09-16 | No required for this prodt, required for all pro
158 | Scale up & AMV | Scale up & AMV | VE3-T154 | VQ Analysis | VE3-T158 | API/RM & PM Spec/STPs at QA | satyanarayana.perabathula | AQA | Waiting for tasks | true | VE3-T156,VE3-T155,VE3-T157 | VE3-T185,VE3-T186,VE3-T187 |  | 2026-09-16
159 | Scale up & AMV | Scale up & AMV | - |  | VE3-T159 | Material procurement for EB | naresh.nalajala | SCM | Blocking tasks | false |  | VE3-T184 |  | 2026-09-16
160 | Scale up & AMV | Scale up & AMV | VE3-T159 | Material procurement for EB | VE3-T160 | RM BOM Finalization | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T163,VE3-T161 |  | 2026-09-16
161 | Scale up & AMV | Scale up & AMV | VE3-T159 | Material procurement for EB | VE3-T161 | API PR | PM | PM | Waiting for tasks | false | VE3-T160 | VE3-T162 |  | 2026-09-16
162 | Scale up & AMV | Scale up & AMV | VE3-T159 | Material procurement for EB | VE3-T162 | API PO to receipt for EB | naresh.nalajala | SCM | Waiting for tasks | false | VE3-T161 | VE3-T185 |  | 2026-09-16
163 | Scale up & AMV | Scale up & AMV | VE3-T159 | Material procurement for EB | VE3-T163 | RM PR | PM | PM | Waiting for tasks | false | VE3-T160 | VE3-T164 |  | 2026-09-16
164 | Scale up & AMV | Scale up & AMV | VE3-T159 | Material procurement for EB | VE3-T164 | RM - PO to receipt | naresh.nalajala | SCM | Waiting for tasks | false | VE3-T163 | VE3-T186 |  | 2026-09-16
165 | Scale up & AMV | Scale up & AMV | VE3-T159 | Material procurement for EB | VE3-T165 | PM BOM Finalization | PM | PM | Blocking tasks | false |  | VE3-T166 |  | 2026-09-16
166 | Scale up & AMV | Scale up & AMV | VE3-T159 | Material procurement for EB | VE3-T166 | PM PR | PM | PM | Waiting for tasks | false | VE3-T165 | VE3-T167 |  | 2026-09-16
167 | Scale up & AMV | Scale up & AMV | VE3-T159 | Material procurement for EB | VE3-T167 | PM - PO to receipt | PM | PM | Waiting for tasks | false | VE3-T166 | VE3-T187 |  | 2026-09-16
168 | Scale up & AMV | Scale up & AMV | - |  | VE3-T168 | Scale up execution | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T134,VE3-T142 | VE3-T202 |  | 2026-09-16
169 | Scale up & AMV | Scale up & AMV | VE3-T168 | Scale up execution | VE3-T169 | Scale up batches execution | sadasivudu.pothana | F R&D | Blocking tasks | true |  | VE3-T170 |  | 2026-09-16
170 | Scale up & AMV | Scale up & AMV | VE3-T168 | Scale up execution | VE3-T170 | Scale up batch analysis | narendra.thamma kumar | F AR&D | Waiting for tasks | true | VE3-T169 | VE3-T171 |  | 2026-09-16
171 | Scale up & AMV | Scale up & AMV | VE3-T168 | Scale up execution | VE3-T171 | Scale up batch report | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T170 | VE3-T203 |  | 2026-09-16
172 | Scale up & AMV | Scale up & AMV | - |  | VE3-T172 | Product Analytical method validation/Transfer | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | false | VE3-T90 |  |  | 2026-09-16
173 | Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T173 | AMV - Feasibility (if required) | rameshbabu.balina Babu | QC 2 GGP | Blocking tasks | false |  | VE3-T174,VE3-T175 |  | 2026-09-16
174 | Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T174 | AMV in-process | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | false | VE3-T101,VE3-T173 | VE3-T177,VE3-T178 |  | 2026-09-16
175 | Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T175 | AMV finished product | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | false | VE3-T101,VE3-T173 | VE3-T177,VE3-T180 |  | 2026-09-16
176 | Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T176 | AMV Forced degradation studies | rameshbabu.balina Babu | QC 2 GGP | Independent tasks | false |  |  |  | 2026-09-16
177 | Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T177 | IP / FP Analytical Method Transfer (if required) | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | false | VE3-T174,VE3-T175 |  |  | 2026-09-16
178 | Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T178 | ARD IP Spec/STPs to QA | narendra.thamma kumar | F AR&D | Waiting for tasks | false | VE3-T174 | VE3-T179 |  | 2026-09-16
179 | Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T179 | QA IP Spec/STPs to QC | satyanarayana.perabathula | AQA | Waiting for tasks | false | VE3-T178,VE3-T206 |  |  | 2026-09-16
180 | Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T180 | ARD FP Spec/STPs to QA | narendra.thamma kumar | F AR&D | Waiting for tasks | false | VE3-T175 | VE3-T181 |  | 2026-09-16
181 | Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T181 | QA FP Spec/STPs to QC | satyanarayana.perabathula | AQA | Waiting for tasks | false | VE3-T180,VE3-T206 |  |  | 2026-09-16
182 | Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T182 | Elemental impurities AMV | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | false | VE3-T103 |  |  | 2026-09-16
183 | Scale up & AMV | Scale up & AMV | VE3-T172 | Product Analytical method validation/Transfer | VE3-T183 | Nitroso impurities AMV | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | false | VE3-T105 |  |  | 2026-09-16
184 | Scale up & AMV | Scale up & AMV | - |  | VE3-T184 | Material readiness for EB | PM | PM | Waiting for tasks | true | VE3-T159,VE3-T154 | VE3-T213 |  | 2026-09-16
185 | Scale up & AMV | Scale up & AMV | VE3-T184 | Material readiness for EB | VE3-T185 | API - Analysis & release for EB | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | true | VE3-T162,VE3-T158 | VE3-T214 |  | 2026-09-16
186 | Scale up & AMV | Scale up & AMV | VE3-T184 | Material readiness for EB | VE3-T186 | RM - Analysis & release for EB | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | true | VE3-T164,VE3-T158 | VE3-T214 |  | 2026-09-16
187 | Scale up & AMV | Scale up & AMV | VE3-T184 | Material readiness for EB | VE3-T187 | PM - Analysis & release for EB | PM | PM | Waiting for tasks | true | VE3-T167,VE3-T158 | VE3-T218 |  | 2026-09-16
188 | Scale up & AMV | Scale up & AMV | - |  | VE3-T188 | L2 Clearances | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  | 2026-09-16
189 | Scale up & AMV | Scale up & AMV | VE3-T188 | L2 Clearances | VE3-T189 | IIG Clearance (L2) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  | 2026-09-16
190 | Scale up & AMV | Scale up & AMV | VE3-T188 | L2 Clearances | VE3-T190 | IPR Clearance (L2) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  | 2026-09-16
191 | Scale up & AMV | Scale up & AMV | VE3-T188 | L2 Clearances | VE3-T191 | Trade dress / Trademark Clearance (L2) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  | 2026-09-16
192 | Scale up & AMV | Scale up & AMV | VE3-T188 | L2 Clearances | VE3-T192 | Size & shape Clearance (L2) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  | 2026-09-16
193 | Scale up & AMV | Scale up & AMV | VE3-T188 | L2 Clearances | VE3-T193 | Costing clearance - Cost/pill (L2) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  | 2026-09-16
194 | Scale up & AMV | Scale up & AMV | - |  | VE3-T194 | Updated Risk assessment | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  | 2026-09-16
195 | Scale up & AMV | Scale up & AMV | VE3-T194 | Updated Risk assessment | VE3-T195 | Updated Residual solvent assessment report (in-case of changes) | narendra.thamma kumar | F AR&D | Independent tasks | false |  |  |  | 2026-09-16
196 | Scale up & AMV | Scale up & AMV | VE3-T194 | Updated Risk assessment | VE3-T196 | Updated Elemental impurity risk assessment report (in-case of changes) | narendra.thamma kumar | F AR&D | Independent tasks | false |  |  |  | 2026-09-16
197 | Scale up & AMV | Scale up & AMV | VE3-T194 | Updated Risk assessment | VE3-T197 | Updated Genotoxic impurity risk assessment report (in-case of changes) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  | 2026-09-16
198 | Scale up & AMV | Scale up & AMV | VE3-T194 | Updated Risk assessment | VE3-T198 | Updated Nitrosamine Risk assessment report (in-case of changes) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  | 2026-09-16
199 | Scale up & AMV | Scale up & AMV | VE3-T194 | Updated Risk assessment | VE3-T199 | Updated Iron Content (in-case of changes) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  | 2026-09-16
200 | Scale up & AMV | Scale up & AMV | - |  | VE3-T200 | Exhibit batch strategy | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  | 2026-09-16
201 | Scale up & AMV | Scale up & AMV | VE3-T200 | Exhibit batch strategy | VE3-T201 | Mfg. process & controls/equipment qualification range evaluation report. | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  | 2026-09-16
202 | Scale up & AMV | Scale up & AMV | - |  | VE3-T202 | Phase gate 4 clearances | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T168 | VE3-T205 |  | 2026-09-16
203 | Scale up & AMV | Scale up & AMV | VE3-T202 | Phase gate 4 clearances | VE3-T203 | Master Formula Card (MFC) | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T171 | VE3-T204 |  | 2026-09-16
204 | Scale up & AMV | Scale up & AMV | VE3-T202 | Phase gate 4 clearances | VE3-T204 | Master Packaging Card (MPC) | PM | PM | Waiting for tasks | true | VE3-T203 | VE3-T206 |  | 2026-09-16
205 | Exhibit batches | Exhibit batches | - |  | VE3-T205 | EB Documentation | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T85,VE3-T202,VE3-T128 | VE3-T213
206 | Exhibit batches | Exhibit batches | VE3-T205 | EB Documentation | VE3-T206 | Change control (initiation to approval) | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T204 | VE3-T207,VE3-T208,VE3-T210,VE3-T211,VE3-T179,VE3-T181,VE3-T209 |  | 2026-09-16
207 | Exhibit batches | Exhibit batches | VE3-T205 | EB Documentation | VE3-T207 | Cleaning validation protocol | PM | PM | Waiting for tasks | false | VE3-T206 |  |  | 2026-09-16
208 | Exhibit batches | Exhibit batches | VE3-T205 | EB Documentation | VE3-T208 | Batch production records | sadasivudu.pothana | F R&D | Waiting for tasks | false | VE3-T206 | VE3-T214
209 | Exhibit batches | Exhibit batches | VE3-T205 | EB Documentation | VE3-T209 | Batch manufacturing records | sadasivudu.pothana | F R&D | Waiting for tasks | false | VE3-T206 | VE3-T216
210 | Exhibit batches | Exhibit batches | VE3-T205 | EB Documentation | VE3-T210 | Batch packing records | PM | PM | Waiting for tasks | false | VE3-T206 | VE3-T218
211 | Exhibit batches | Exhibit batches | VE3-T205 | EB Documentation | VE3-T211 | Exhibit batch protocols (Sampling/Hold time) | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T206 | VE3-T216,VE3-T214
212 | Exhibit batches | Exhibit batches | VE3-T205 | EB Documentation | VE3-T212 | Stability protocols | satyanarayana.perabathula | AQA | Waiting for tasks | true | VE3-T218 |  |  | 2026-08-05
213 | Exhibit batches | Exhibit batches | - |  | VE3-T213 | EB Manufacturing | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T184,VE3-T205 | VE3-T220,VE3-T256,VE3-T257 |  | 2026-09-17
214 | Exhibit batches | Exhibit batches | VE3-T213 | EB Manufacturing | VE3-T214 | Exhibit batch manufacturing - Blend stage | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T208,VE3-T185,VE3-T186,VE3-T211 | VE3-T216,VE3-T215 |  | 2026-09-17
215 | Exhibit batches | Exhibit batches | VE3-T213 | EB Manufacturing | VE3-T215 | Exhibit batch IP Stage testing & release | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | true | VE3-T214 | VE3-T216 |  | 2026-09-17
216 | Exhibit batches | Exhibit batches | VE3-T213 | EB Manufacturing | VE3-T216 | Exhibit batch manufacturing - FP Stage | sadasivudu.pothana | F R&D | Waiting for tasks | true | VE3-T209,VE3-T211,VE3-T214,VE3-T215 | VE3-T217,VE3-T218 |  | 2026-09-17
217 | Exhibit batches | Exhibit batches | VE3-T213 | EB Manufacturing | VE3-T217 | Exhibit batch FP Stage testing & release | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | false | VE3-T216 | VE3-T219 |  | 2026-09-17
218 | Exhibit batches | Exhibit batches | VE3-T213 | EB Manufacturing | VE3-T218 | Exhibit batch packaging | PM | PM | Waiting for tasks | true | VE3-T187,VE3-T210,VE3-T216 | VE3-T212,VE3-T219 |  | 2026-09-17 | 19
219 | Exhibit batches | Exhibit batches | VE3-T213 | EB Manufacturing | VE3-T219 | Stability date in | satyanarayana.perabathula | AQA | Waiting for tasks | true | VE3-T217,VE3-T218 | VE3-T221,VE3-T235,VE3-T236 |  | 2026-09-19 | 15
220 | Exhibit batches | Exhibit batches | - |  | VE3-T220 | EB Sample analysis | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | false | VE3-T213
221 | Exhibit batches | Exhibit batches | VE3-T220 | EB Sample analysis | VE3-T221 | EB Protocol bound sample data generation | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | false | VE3-T219 | VE3-T251 |  | 2026-12-19
222 | Exhibit batches | Exhibit batches | - |  | VE3-T222 | Other studies on EB Samples | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  | 2026-12-19
223 | Exhibit batches | Exhibit batches | VE3-T222 | Other studies on EB Samples | VE3-T223 | In-use stability studies Initiation | satyanarayana.perabathula | AQA | Waiting for tasks | false | VE3-T219 |  |  | 2026-10-04 | Add
224 | Exhibit batches | Exhibit batches | VE3-T222 | Other studies on EB Samples | VE3-T224 | Photostability studies | rameshbabu.balina Babu | QC 2 GGP | Independent tasks | false |  |  |  |  | Not for this prod
225 | Exhibit batches | Exhibit batches | VE3-T222 | Other studies on EB Samples | VE3-T225 | Split studies | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  |  | Not for this prod
226 | Exhibit batches | Exhibit batches | VE3-T222 | Other studies on EB Samples | VE3-T226 | Alcohol dose dumping studies (if applicable) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  |  | Not for this prod
227 | Exhibit batches | Exhibit batches | VE3-T222 | Other studies on EB Samples | VE3-T227 | Transportation studies | sadasivudu.pothana | F R&D | Independent tasks | false
228 | Exhibit batches | Exhibit batches | VE3-T222 | Other studies on EB Samples | VE3-T228 | XRD data generation | rameshbabu.balina Babu | QC 2 GGP | Independent tasks | false
229 | Exhibit batches | Exhibit batches | - |  | VE3-T229 | Pivotal BE Preparation | Ayyappa Kapuganti | BE Study Coordinator | Waiting for tasks | false | VE3-T128 | VE3-T240
230 | Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T230 | Pivotal BE Study Protocols readiness | Ayyappa Kapuganti | BE Study Coordinator | Blocking tasks | false |  | VE3-T232 |  | 2026-05-05
231 | Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T231 | BENOC documents submission | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T232 |  | 2026-05-15
232 | Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T232 | Test license/BENOC for pivotal BE | Ayyappa Kapuganti | BE Study Coordinator | Waiting for tasks | false | VE3-T230,VE3-T231 |  |  | 2026-06-15
233 | Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T233 | RLD for Pivotal BE studies | PM | PM | Blocking tasks | false |  | VE3-T234 |  | 2026-05-05
234 | Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T234 | RLD COA generation | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | false | VE3-T233 |  |  | 2026-09-17
235 | Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T235 | Test (EB) & RLD 12 units release medium dissolution | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | false | VE3-T219 | VE3-T237 |  | 2026-12-19
236 | Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T236 | Test (EB) & RLD 12 units multi media dissolutions | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | false | VE3-T219 | VE3-T237 |  | 2026-12-19
237 | Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T237 | Note for approval for Pivotal BE (Technical) | sadasivudu.pothana | F R&D | Waiting for tasks | false | VE3-T235,VE3-T236 | VE3-T238 |  | 2026-09-29
238 | Exhibit batches | Exhibit batches | VE3-T229 | Pivotal BE Preparation | VE3-T238 | Note for approval for Pivotal BE (Budget & PR, PO) | PM | PM | Waiting for tasks | false | VE3-T237 |  |  | 2026-10-10
239 | Pivotal BE studies | Pivotal BE | - |  | VE3-T239 | Phase gate 5 clearance | sadasivudu.pothana | F R&D | Independent tasks | false
240 | Pivotal BE studies | Pivotal BE | - |  | VE3-T240 | Pivotal BE Studies | Ayyappa Kapuganti | BE Study Coordinator | Waiting for tasks | false | VE3-T229 | VE3-T259 |  | 2027-01-13
241 | Pivotal BE studies | Pivotal BE | VE3-T240 | Pivotal BE Studies | VE3-T241 | BE samples shipment to CRO | Ayyappa Kapuganti | BE Study Coordinator | Blocking tasks | false |  | VE3-T242,VE3-T244 |  | 2026-10-12
242 | Pivotal BE studies | Pivotal BE | VE3-T240 | Pivotal BE Studies | VE3-T242 | Fasting pivotal study (Clinic start - End) | Ayyappa Kapuganti | BE Study Coordinator | Waiting for tasks | false | VE3-T241 | VE3-T243 |  | 2026-11-27
243 | Pivotal BE studies | Pivotal BE | VE3-T240 | Pivotal BE Studies | VE3-T243 | Fasting study results | Ayyappa Kapuganti | BE Study Coordinator | Waiting for tasks | false | VE3-T242 |  |  | 2026-12-13
244 | Pivotal BE studies | Pivotal BE | VE3-T240 | Pivotal BE Studies | VE3-T244 | Fed pivotal study (Clinic start - End) | Ayyappa Kapuganti | BE Study Coordinator | Waiting for tasks | false | VE3-T241 | VE3-T245 |  | 2027-01-13
245 | Pivotal BE studies | Pivotal BE | VE3-T240 | Pivotal BE Studies | VE3-T245 | Fed Study results | Ayyappa Kapuganti | BE Study Coordinator | Waiting for tasks | false | VE3-T244 |  |  | 2027-01-28
246 | Pivotal BE studies | Pivotal BE | VE3-T240 | Pivotal BE Studies | VE3-T246 | Other studies if any | Ayyappa Kapuganti | BE Study Coordinator | Independent tasks | false
247 | Pivotal BE studies | Pivotal BE | - |  | VE3-T247 | Any other studies (Suspension/NG tube /Apple sauce etc..) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  |  | Only for KCL
248 | Dossier filing | Filing | - |  | VE3-T248 | L3 Clearances | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  | 2026-11-19
249 | Dossier filing | Filing | VE3-T248 | L3 Clearances | VE3-T249 | Costing clearance (L3) | sadasivudu.pothana | F R&D | Independent tasks | false
250 | Dossier filing | Filing | - |  | VE3-T250 | Intended Documents readiness | balakrishna.kurra | balakrishna.kurra | Blocking tasks | false |  | VE3-T259
251 | Dossier filing | Filing | VE3-T250 | Intended Documents readiness | VE3-T251 | EB reports availability | sadasivudu.pothana | F R&D | Waiting for tasks | false | VE3-T221 | VE3-T252 |  | 2026-12-29
252 | Dossier filing | Filing | VE3-T250 | Intended Documents readiness | VE3-T252 | Master Formula Record readiness | balakrishna.kurra | balakrishna.kurra | Waiting for tasks | false | VE3-T251 | VE3-T253 |  | 2027-01-09
253 | Dossier filing | Filing | VE3-T250 | Intended Documents readiness | VE3-T253 | Intended Docs preparation | balakrishna.kurra | balakrishna.kurra | Waiting for tasks | false | VE3-T252 |  |  | 2027-01-19
254 | Dossier filing | Filing | - |  | VE3-T254 | PDR readiness | sadasivudu.pothana | F R&D | Blocking tasks | false |  | VE3-T259 |  | 2027-02-03
255 | Dossier filing | Filing | - |  | VE3-T255 | Pivotal BE studies report availability | Ayyappa Kapuganti | BE Study Coordinator | Independent tasks | false |  |  |  | 2027-02-23
256 | Dossier filing | Filing | - |  | VE3-T256 | 3M stability data availability | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | false | VE3-T213 |  |  | 2027-02-01
257 | Dossier filing | Filing | - |  | VE3-T257 | 6M stability data availability | rameshbabu.balina Babu | QC 2 GGP | Waiting for tasks | true | VE3-T213 | VE3-T259 |  | 2027-05-02
258 | Dossier filing | Filing | - |  | VE3-T258 | Phase gate 6 clearance (Costing, docs as per RA checklist ) | sadasivudu.pothana | F R&D | Independent tasks | false |  |  |  | 2027-02-03
259 | Dossier filing | Filing | - |  | VE3-T259 | Filing | RA | RA | Waiting for tasks | true | VE3-T250,VE3-T254,VE3-T240,VE3-T257 |  |  | 2027-02-11