## Risk Reg.
Risk Register
Project name:
Project manager:
ID | Date raised | Risk description | Likelihood of the risk occurring (1,2,3,4) | Impact if the risk occurs (1,2,3,4) | Severity Rating based on impact & likelihood. | Owner Person who will manage the risk. | Mitigating action Actions to mitigate the risk e.g. reduce the likelihood. | Contingent action Action to be taken if the risk happens. | Progress on actions | Status
1 | [enter date] | Project purpose and need is not well-defined. | 1 | 4 | High | Project Sponsor | Complete a business case if not already provided and ensure purpose is well defined on Project Charter and PID. | Escalate to the Project Board with an assessment of the risk of runaway costs/never-ending project. | Business case re-written with clear deliverables and submitted to the project board for approval. | Open

## Opportunities
Opportunity Register
Opp. ID | Date Identified (dd-mm-yyyy) | Description | Potential Benefits | Cost | Benefit | CBA Priority (Cost*Benefit) | Opportunity Leverage Strategy | Action | Ownership | Target Closure Date (dd-mm-yyyy) | Status | Remark (If any)
|  |  |  | Low | Low | Medium |  |  |  |  | INPR
|  |  |  | High | Low | Low |  |  |  |  | Closed
|  |  |  | Low | Medium | High |  |  |  |  | Lead
|  |  |  | Medium | High | High
|  |  |  | Select | Select | NA
|  |  |  | Select | Select | NA
|  |  |  | Select | Select | NA
|  |  |  | Select | Select | NA
|  |  |  | Select | Select | NA

## Guidelines
Risk ANALYSIS |  | Opportunity ANALYSIS |  | POTENTIAL BENEFIT
Probability - Likelihood of Occurrence | Level |  |  | Low | Medium | High
Remote / Unlikely | 1 | POTENTIAL COST | Low | Medium | High | High
Likely | 2 |  | Medium | Low | Medium | High
Highly likely | 3 |  | High | Low | Low | Medium
Near Certainty | 4
Consequences / Impact | Impact value
Negligible | 1
Marginal | 2
Critical | 3
Catastrophic | 4
Risk categorization on the basis of derived Exposure (Impact * Probability)
Exposure | Risk Categorization
between 1 - 5 | Low
between 6 - 11 | Moderate
More than 11 | High

## Issue Tracker
Issue Tracker
S. No. | Project | Issue description | Potential Impact | Priority | Date Opened | Date Closed | Issue Owner | Department | Status | Notes
1 |  |  |  | Critical |  |  |  | ACE | Open
2 |  |  |  | Low |  |  |  | Service | Open
3 |  |  | Accuracy not meeting acceptance criteria | Medium |  |  | Varun | ACE | Open | Need to send updated deck to Business
High

## Risk Register (hidden)
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11

## Sheet1 (hidden)
Action Items
Sr.No | Action Item | Owner | Expected Date | Status | Remarks
1 | Conducting of Data Science Training | KPMG | 16/2/2021 | In-Progress | Although session#1 was conducted on the 17th Feb,session#2 is reuqested, in which the concept could be explained with an example that would help us to understand the methodology being followed by KPMG in this particular project .
2 | Requirements Confirmation | KPMG | 15/2/2021 | In-Progress | Model output, forecast drill-down, model base line accuracy & confidence level, KPI list, feature list along with business outcome & success criteria to be discussed and finalized.
3 | Requirements Confirmation | KPMG | 17/2/2021 | In-Progress | Wireframe Design Finalisation is underway.
4 | Data Ingestion (Data Science) | KPMG | 18/2/2021 | In-Progress | Data Source connectivity testing & Modularized Script Development for Data Ingestion is underway.