## Project Plan
Document Type: Template |  | Document ID: DE/ACE/TMP/003
Document Name: Estimation |  | Revision Number:
Revision Date:
Project Title: |  |  |  |  | Project Start Date: | 2021-09-20
[5 empty] | Display: | Weekly
[5 empty] | Display Period: | 5
Stakeholders:
PHASES | S.No. | ACTIVITIES | COMMENTS | RESPONSIBILITY | PROGRESS(% Completion) | PLANNED START | PLANNED END | PLAN MANDAY EFFORT | ACTUAL START | ACTUAL END | ACTUAL MANDAY EFFORT
Project Initiation |  | Vendor Selection |  |  | 100% | 2021-09-08 | 2021-09-11 | 3 | 2021-09-08 | 2021-09-11 | 4
|  | Ringi Approval |  |  | 100% | 2021-09-08 | 2021-09-10 | 3 | 2021-09-08 | 2021-09-10 | 3
SOW finalization
Requirement Gathering
Requirement Document Preparation
Requirement Document Review
Data Exploration & Transformation |  | Custom Dataset Prototyping
Dataset Prototype Review and Feedback
Data Modelling |  | Data Modelling
Data Modelling Review
Validation
Data Model Re-caliberation
Production Deployment

## Risk Register (hidden)
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11

## Sheet1 (hidden)
Action Items
Sr.No | Action Item | Owner | Expected Date | Status | Remarks
1 | Conducting of Data Science Training | KPMG | 16/2/2021 | In-Progress | Although session#1 was conducted on the 17th Feb,session#2 is reuqested, in which the concept could be explained with an example that would help us to understand the methodology being followed by KPMG in this particular project .
2 | Requirements Confirmation | KPMG | 15/2/2021 | In-Progress | Model output, forecast drill-down, model base line accuracy & confidence level, KPI list, feature list along with business outcome & success criteria to be discussed and finalized.
3 | Requirements Confirmation | KPMG | 17/2/2021 | In-Progress | Wireframe Design Finalisation is underway.
4 | Data Ingestion (Data Science) | KPMG | 18/2/2021 | In-Progress | Data Source connectivity testing & Modularized Script Development for Data Ingestion is underway.